For GFIs

CY 2012 ODA PORTFOLIO REVIEW

Project Factsheet

As of December 31, 2012

| LOAN/GRANT DATA Project Title Fund Source Loan/Grant Number Loan/Grant Amount Signing Date Effectivity Date Closing Date Interest Rate Service Charge Commitment Charge/Fee Maturity Period Grace Period Cancellation Amount Cancelled Date Cancelled Implementing Agency Sector/Sub-sector Region(s) Province(s) Beneficiaries Objective(s) Description PROJECT COMPONENTS Components Output Indicators Cost Target at end of Project Original Revised PROJECT COST Total Forex Local Conversion Rate ICC-Approved Cost Loan/Grant Agreement Cost Revised ICC-Approved Cost Loan Proceeds Grant Proceeds GOP IMPLEMENTATION SCHEDULE Project Start Date Physical Completion Date | Pertinent data based on loan/grant document As indicated in loan/grant agreement Name of funding institution where loan/grant proceeds was sourced As indicated in loan/grant agreement Amount of loan/grant indicated in loan/grant agreement, expressed in original currency of funding institution Date when loan/grant agreement was signed (mm/dd/yyyy) Date when loan/grant proceeds can be released by the funding institution to borrower upon its compliance with pre-conditions for loan effectivity (mm/dd/yyyy) Date of loan/grant expiration further classified into original and revised (mm/dd/yyyy) Charge made by funding institution to borrower for the use of the loan, in percent Or handling charge; charge made by funding institution to borrower for every disbursement made from the loan proceeds as indicated in the loan agreement Charge made by funding institution to borrower for holding available the undisbursed balance or undrawn amount of a loan commitment Period at which the final repayment of a loan is due; a measure of the scheduled life of a loan (or grace period plus repayment period), number of years Period commencing from the time the loan agreement was signed up to the time the initial principal repayment becomes due, number of years Actual amount deducted from loan by funding institution, as mutually agreed upon with borrower, expressed in original currency of funding institution Date when loan amount was cancelled (mm/dd/yyyy) Name of agency(ies) implementing the project Sectoral/sub-sectoral classification of the project Regional location where project will be implemented and/or being implemented Provincial location where project will be implemented and/or being implemented Target group of people where the project is planned to bring benefits, and quantity to the extent possible Brief description of the new conditions that will be realized/achieved upon project completion, when beneficiaries utilize the project outputs Brief project description to cover overall physical output, project components, inputs and other important aspects of the project. (Please limit to a maximum of 50 words) Components of the project as identified in project documents Major output indicator per component where accomplishment is to be measured as identified in project document Equivalent cost of components identified in project documents or project appraisal reports, in P million Target quantity to be accomplished per major output indicator as originally agreed between implementing agency and funding institution based on approved project documents or project appraisal reports Adjusted target to be accomplished per major output indicator based on revised plan as agreed between implementing agency and funding institution, as approved by the Investment Coordination Committee (ICC). Sum of Foreign Exchange component in peso equivalent and Local cost of the project, in P million. Foreign Exchange requirement of the project, in P million Local cost requirement of the project, in P million Peso equivalent of one (1) US$ or currency of funding institution (whichever is applicable). Cost indicated in original ICC-approved document, in P million Cost indicated in the loan/grant agreement, in P million Revised project cost as approved by ICC, indicate date of ICC concurrence and/or re-appraisal, in P million and mm/dd/yyyy Sum of loan proceeds expressed in original currency of the funding institution Sum of grant proceeds expressed in original currency of the funding institution Sum of GOP counterpart funds from GFI and sub-borrowers, in P million Date when project is scheduled to start as agreed between the implementing agency and funding institution (mm/yyyy) Date when project is scheduled to be completed as agreed between implementing agency and funding institution, classified as ‘Original’ and ‘Revised’ (mm/yyyy) |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 1A

Regional Disaggregation of Projects

GFI Name

As of December 31, 2012

| PROJECT TITLE LOCATION PROJECT COST TP LP GP GOP IMPLEMENTATION SCHEDULE Start Completion REMARKS | As indicated in loan/grant agreement Regional location where project will be implemented and/or being implemented Sum of funds from loan and grant proceeds and peso counterpart, in P million. Amount financed by loan from funding institution, in P million Amount financed by grant from funding institution, in P million Local counterpart of the project, in Pmillion Date when project is scheduled to start as agreed between the implementing agency and the funding institution (mm/dd/yyyy) Date when project is scheduled to be completed as agreed between implementing agency and funding institution, classified as ‘Original’ and ‘Revised’ (mm/yyyy) Justifications/explanations for any deviations, if any, in the project cost and implementation schedule as compared with those indicated in the Project Factsheet, and issues/problems encountered which resulted in said deviation |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 1B

Project(s)/ Component(s) Supportive of the Achievement of the MDGs

GFI Name

As of December 31, 2012

| PROJECT TITLE Component MILLENNIUM DEVELOPMENT GOALS | As indicated in loan/grant agreement Components of the project as identified in project documents A set of eight time-bound, concrete and specific targets to reduce poverty by 2015 (UNDP). These goals were agreed upon by 192 United Nations (UN) member states in September 2000. The MDGs aim to spur development by improving social and economic conditions in the world’s poorest countries. |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 1C

Project(s)/Component(s) Addressing Climate Change and Contributing to Disaster Risk Reduction

GFI Name

As of December 31, 2012

| PROJECT TITLE Component Mitigation Adaptation DISASTER RISK REDUCTION (DRR) | As indicated in loan/grant agreement Components of the project as identified in project documents Aims to facilitate the transition towards low greenhouse gas emissions for sustainable development a) energy efficiency and conservation; b) realization of the full potential of the country’s renewable energy; c) improvement of the transport sector through the uptake of alternative fuels and expansion of mass transport systems; d) making use of energy--efficient design and materials for public infrastructure and settlements; e) reduction of emissions from deforestation and forest degradation; and g) waste management. Points towards building the adaptive capacity of communities and increasing the resilience of natural ecosystems to climate change a) enhancement of vulnerability and adaptation assessments; b) integrated ecosystem-based management; c) water governance and management; d) promotion of a climate-responsive agriculture; e) support climate-responsive health sector; f) encourage climate-proofing infrastructure; and g) disaster risk reduction. The ADB defines DRR as a “series of interconnected actions to minimize disaster vulnerability by avoiding (prevention) or limiting (mitigation and preparedness) the adverse effects of hazards within the broad context of sustainable development.” DRR is also an integral component of CC adaptation. A comprehensive approach for DRR is set out in the UN-endorsed Hyogo Framework for Action (HFA). It highlights five priority areas of action: (1) Ensure that disaster risk reduction is a national and a local priority with a strong institutional basis for implementation; (2) Identify, assess, and monitor disaster risks and enhance early warning; (3) Use knowledge, innovation, and education to build a culture of safety and resilience at all levels; (4) Reduce the underlying risk factors; and, (5) Strengthen disaster preparedness for effective response at all levels. |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 2

Budget Forecast and Physical Targets

GFI Name

As of December 31, 2012

| PROJECT TITLE TOTAL COST ICC-Approved Cost ALLOCATION As of December 31, 2011 CY2012 MULTI-YEAR REQUIREMENT FORECAST ACTUAL PHYSICAL ACCOMPLISHMENT As of December 31, 2011 CY2012 PROJECTED PHYSICAL ACCOMPLISHMENT | As indicated in loan/grant agreement ICC-Approved Cost and Loan Agreement (L/A) Cost, classified as funds from loan proceeds and GOP counterpart, in P million Project cost indicated in ICC-approved document further classified into ‘Original’ and ‘Revised’, in P million Project cost indicated in loan/grant agreement, in P million Authorization issued by the GFI Board, which allows an agency to incur obligations for specified amounts, classified into funds provided through loan proceeds and GOP counterpart Cumulative total approved allocation since project start up to December 2011, in P million Approved allocation for the reporting period, in P million Projected financial requirements per year from CY2013 to CY2017, and future years, classified as loan proceeds and GOP counterpart, Pmillion Actual physical accomplishment since the start of the project up to the end of December 2011, in % Actual physical accomplishment during the particular reporting period, in %. Physical targets for the remaining years from CY2013 to CY2017, and future years, in %. In case annual physical targets could not be expressed in overall percentage, please indicate target, based on output indicators |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 3A

Financial Status of Projects

GFI Name

As of December 31, 2012

| PROJECT TITLE ALLOCATION As of December 31, 2011 CY2012 OBLIGATIONS As of December 31, 2011 CY2012 EXPENDITURES As of December 31, 2011 CY2012 | As indicated in loan/grant agreement Authorization issued by the GFI Board, which allows an agency to incur obligations for specified amounts, classified into funds provided through loan and grant proceeds and GOP counterpart Cumulative amount approved from start of the project up to end of CY 2011, in Pmillion Amount approved for the reporting period, in Pmillion Liabilities legally incurred and committed to be paid by the agency either immediately or in the future to the sub-borrowers Cumulative obligations incurred from the start of the project up to the end of CY2011, in P million Obligations incurred by the project for the reporting period, in P million Actual amount expended for the project Cumulative actual amount expended/utilized by the project from the start of the project up to end of CY2011, in P million Actual amount expended/utilized by the project for the reporting period, in P million |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 3B

Physical Targets and Actual Accomplishments of Projects

GFI Name

As of December 31, 2012

| PROJECT TITLE TARGET As of December 31, 2011 CY2012 ACTUAL As of December 31, 2011 CY2012 SLIPPAGE As of December 31, 2011 CY2012 REMARKS | As indicated in loan/grant agreement Estimated physical targets which could be derived from the project S-curve. In case annual physical targets could not be expressed in overall percentage, please indicate target, based on output indicators Cumulative target since the start of the project up to the end of CY 2011, in % Physical target or output during the particular reporting period, in % Overall physical accomplishment or output of the project Cumulative physical accomplishment or output since the start of the project up to the end of December 2011, in % Physical accomplishment or output during the particular reporting period, in %. Variance between target and actual physical accomplishment or output of the project Overall slippage since the start of the project up to the end of CY 2011, in % Slippage of the project during the particular reporting period, in %. Indicate whether the project would be completed on schedule, or when slippage occurs, the extent and factors causing such slippage. In case no physical accomplishment or output was generated as of the reporting period, please indicate preparatory activities being undertaken such as: (1) preparation of work plan/financial requirements; (2) selection of consultants; etc. Please indicate also the status of said activities. |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 3C

Loan Disbursement Targets

GFI Name

As of December 31, 2012

| PROJECT TITLE NET COMMITMENT DISBURSEMENTS as of December 2012 2013 TARGETS Q1 Q2 Q3 Q4 FUTURE TARGETS 2014 2015 2016 Future years TOTAL | As indicated in loan agreement Total loan amount less cumulative partial cancellations (This data may be requested from NEDA PMS project officers) Cumulative loan drawdowns as registered with the fund source from project start to reporting period (This data may be requested from NEDA PMS project officers) Disbursement targets for January 1 to December 31, 2013. Note that in calculating disbursement targets, the project must take into account the definition of disbursement, which means loan drawdown for a period as registered with the fund source. Disbursement under this definition may not yet entail actual payment by the agency to providers of goods and services. Thus, future payment by the agency to providers, when already registered as disbursement with the fund source during a previous period, should no longer be included in the loan disbursement targeting. Disbursement target for January to March 2013 Disbursement target for April to June 2013 Disbursement target for July to September 2013 Disbursement target for October to December 2013 Disbursement target for January to December 2014 Disbursement target for January to December 2015 Disbursement target for January to December 2016 Disbursement target for January 2017 up to the end of the project Sum of disbursements as of December 2012 (Column 2), 2013 Targets (Column 3) and Future Targets (Column 4). The total should equate or not exceed the net commitment (Column 1). |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 3D

Project Disbursement Targets in Peso

GFI Name

As of December 31, 2012

| PROJECT TITLE PROJECT COST ICC-Approved Cost DISBURSEMENTS as of December 2012 2013 TARGETS Q1 Q2 Q3 Q4 FUTURE TARGETS 2014 2015 2016 Future years TOTAL | As indicated in loan agreement ICC-Approved Cost and Loan Agreement (L/A) Cost, classified as funds from loan proceeds and GOP counterpart, in P million Project cost indicated in ICC-approved document further classified into ‘Original’ and ‘Revised’, in P million Cumulative loan drawdowns in P million, from project start to reporting period Disbursement targets in P million from January 1 to December 31, 2013. Disbursement target for January to March 2013 Disbursement target for April to June 2013 Disbursement target for July to September 2013 Disbursement target for October to December 2013 Disbursement target for January to December 2014 Disbursement target for January to December 2015 Disbursement target for January to December 2016 Disbursement target for January 2017 up to the end of the project Sum of the P million disbursements as of December 2012 (Column 2), 2013 Targets (Column 3) and Future Targets (Column 4). |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 4A

Physical Outputs of Projects

GFI Name

As of December 31, 2012

| PROJECT TITLE OUTPUT INDICATOR TARGET As of December 31, 2011 CY2012 ACTUAL As of December 31, 2011 CY2012 REMARKS | As indicated in loan/grant agreement Major output indicator per component where accomplishment is to be measured as indicated in project documents, i.e., number of SMEs provided/extended with loans (DBP), number of LGUs provided/extended with loans (LBP), etc. Target quantity to be accomplished as agreed between implementing agency and funding institution, if any Cumulative quantity to be accomplished from the start of the project up to the end of CY 2011 Target quantity to be accomplished during the particular reporting period Cumulative actual quantity accomplished from the start of the project up to the end of December 2011 Actual quantity accomplished during the particular reporting period Indicate whether the target quantity would be delivered as scheduled, and if not, the factors that affected its delivery on time |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 4B

Project(s) with Damaged Output(s), Incomplete Output(s) and Sustainability Issue(s)

GFI Name

As of December 31, 2012

| PROJECT TITLE YEAR COMPLETED DESCRIPTION OF DAMAGED OUTPUT(S) DESCRIPTION OF INCOMPLETE OUTPUT(S) DESCRIPTION OF SUSTAINABILITY ISSUE(S) ACTIONS TAKEN/ BEING TAKEN | As indicated in loan/grant agreement Date of physical completion of the project (mm/dd/yyyy) Detailed account of the projects’ damaged output(s). Includes which project output(s) were damaged, the extent of the damage as well as factor(s) that caused the damage. Detailed account of loans closed in CY 2012 but with incomplete output(s). Includes which output(s) were not completely delivered and the factor(s) that caused the incomplete delivery of output(s) Detailed account of the issue(s) related to the project’s sustainability. Includes the factor(s) affecting the project sustainability. Identify the action plan by the agency to address the damaged output(s), incomplete output(s), and issue(s) on sustainability |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 5

Estimate of Additional Budget Requirements

(For Projects with Cost Increases)

GFI Name

As of December 31, 2012

| FUNDING SOURCE PROJECT TITLE PROJECT COST ICC-Approved Cost L/A Cost Current Estimate COST OVERRUN ICC-Approved Cost L/A Cost Current Estimate % COST OVERRUN ICC-Approved Cost L/A Cost Current Estimate JUSTIFICATION/REMARKS | Name of funding institution where loan proceeds was sourced As indicated in loan agreement ICC-approved cost, loan agreement cost and current estimate, classified as funds from loan proceeds and GOP counterpart, in P million Project cost as approved by ICC further classified as Original and Revised, in P million Project cost as indicated in the loan agreement, in P million Estimated revised project cost, subject to ICC approval, in P million Estimated additional budget required to complete the project Variance between the original and revised ICC-approved costs, in P million Variance between the original ICC-approved and loan agreement costs, in P million Variance between the ICC- approved and current estimated costs, in P million Percentage of additional budget required to complete the project Percentage variance between the original and revised ICC-approved costs Percentage variance between the ICC- approved and loan agreement costs Percentage variance between the ICC- approved and current estimated costs Explanations or reasons for cost overrun. If the project has been presented to/approved by ICC, please indicate date of concurrence and major reasons cited for cost overrun. |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 6

Problem Analysis of Projects

GFI Name

As of December 31, 2012

| PROJECT TITLE OUTSTANDING PROBLEMS REMARKS/ASSESSMENT ACTION TAKEN/BEING TAKEN RECOMMENDATION/S | As indicated in loan/grant agreement Major issues/problems still outstanding encountered during the pre-implementation phase as well as in the implementation phase. Provide more details on the type/nature of problem, magnitude, as well as indication of how long this problem had been existing. Indicate probable cause of problems and the steps taken/being taken in resolving past problems. Also indicate date(s) when these problems were resolved. List down countermeasures underway or being instituted by concerned unit(s), whether individually or collectively to resolve the identified problems. Indicate details of the problem and its probable effect on the overall project scope, implementation schedule and cost. Indicate also the names of other agencies involved to facilitate early resolution of problems. Outline the action plan necessary to resolve any outstanding problem affecting the project. Given the problems identified as outstanding, indicate the probability of still meeting the project objectives – low, moderate, high probability, etc. |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

TABLE 7A

Projects with Possible Cancellations in CY 2013 and Beyond

GFI Name

As of December 31, 2012

| FUNDING SOURCE PROJECT TITLE POSSIBLE LOAN AMOUNT FOR CANCELLATION IN 2013 AND BEYOND REASON/S FOR CANCELLATION | Name of funding institution where loan proceeds was sourced As indicated in loan agreement Estimated portion of loan amount to be cancelled in 2013 and beyond, in $million Provide details on the reason(s) for cancellation. Given the reasons identified which resulted in the cancellation, indicate the probability of still meeting the project objectives – low, moderate, high probability, etc. |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

TABLE 7B

Projects with Possible Extensions in CY 2013 and Beyond

GFI Name

As of December 31, 2012

| FUNDING SOURCE PROJECT TITLE POSSIBLE LENGTH OF EXTENSION IN 2013 AND BEYOND REASON/S FOR EXTENSION | Name of funding institution where loan proceeds was sourced As indicated in loan agreement Estimated length of extension (in months) in 2013 and beyond, in $million Provide details on the reason(s) for extension. |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 8A

Project Results

GFI Name

As of December 31, 2012

| PROJECT TITLE LOAN/GRANT NUMBER IMPLEMENTING AGENCY PROJECT OBJECTIVE/S RESULTS INDICATORS/TARGET OBSERVED RESULTS | As indicated in loan/grant agreement Number of loan/grant indicated in loan/grant agreement Name of agency(ies) implementing the project Consists of the Goal, Purpose and Output as indicated in the project’s logical framework (ICC PE Form 6). The objectives (if there are many objectives) that will be assessed are those which can be achieved during the evaluation period. Results refer to the project objective(s) as stated in the narrative summary of the project’s logical framework (ICC PE Form 6). These are new conditions or qualities achieved when beneficiaries adopt/utilize the project outputs. Indicators which will measure/indicate in concrete, observable and objectively verifiable terms, to what extent the expected results have been achieved. Indicators, as much as possible, should have Quality, Quantity, Area and Beneficiaries dimensions. Maybe either proxy or logframe indicators. Proxy indicators may lead as “stand in” for the logical framework indicators (as indicated in the project’s logical framework or ICC PE Form 6) whenever the latter is still not available/appreciable but nevertheless may provide early evidence that project results will be or will not be achieved. |
| --- | --- |

Note:	Projects are not simply a means to accomplish components and activities but they are the best means to attain end of project objectives or project results (or outcomes).  Project results are the initial benefits directly resulting from the project.  These should become visible during, or soon, after project completion.  They are usually based on specific results indicators which are measurable indicators derived from the logical framework (or similar instruments) used in the design of the project.

CY 2012 ODA PORTFOLIO REVIEW

Table 8B

Project Results Based on Agency Validated Major Final Outputs (MFOs)

GFI Name

As of December 31, 2012

| VALIDATED MFO PROJECT RESULTS/OUTPUTS COMPLETED PROJECTS TARGET ACTUAL ONGOING PROJECTS TARGET ACTUAL REMARKS | Revised/validated Major final Outputs of the agency Project outputs delivered by the project as of Dec 2011 Name of agency(ies) implementing the project List down outputs of completed projects that contributes to the achievement of the validated agency MFO Target number/quantity of accomplishment Actual number/quantity of accomplishment List down outputs of ongoing projects that contributes to the achievement of the validated agency MFO Target number/quantity of accomplishment Actual number/quantity of accomplishment May state reason/s for not achieving the target number of desired outputs. |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 8C

Project Results Based on Results Matrices (RM) of the

Philippine Development Plan (PDP) 2011-2016

GFI Name

As of December 31, 2012

| PROJECT TITLE LOAN/GRANT NUMBER GFI NAME PDP RM Indicators Relevant to the Project PROJECT RESULTS AS OF DECEMBER 2012 LOCATION AND NO. OF BENEFECIARIES | As indicated in loan/grant agreement Number of loan/grant indicated in loan/grant agreement Name of agency(ies) implementing the project Consist of Sector Goal/s, subsector outcome/s, or intermediate outcome/s as indicated in the PDP RM 2011-2016. In the sample project (Women's Health and Safe Motherhood Project 2/DOH), the RM indicator/s can be found in Chapter 8 (Social Development): Subsector outcome: Contraceptive Prevalence Rate (CPR) increased from 51% in 2008 to 63% in 2015. Reason/s should be provided if the column on RM indicators is not filled out. Indicate absolute value from baseline to 2012, including % of increase. CPR increased from 35% in 2009 to 38% in 2010 or an increase of 3 percentage points. Provide list of locations and no. of beneficiaries to show extent of achievement of results. |
| --- | --- |

CY 2012 ODA PORTFOLIO REVIEW

Table 9A

Procurement Milestones

(With contracts awarded or NTP issued in CY 2012)

GFI Name

As of December 31, 2012

| Project Title Implementing Agency Contract Name/Procurement Guidelines Used Contract Description Start of Tendering Process/Advertisement Submission and Opening of Bids Completion of Bid Evaluation Contract Award Issuance of Notice to Proceed (NTP) Total Concurrence of Funding Institution Net of Funding Institution’s Processing Time | As indicated in loan/grant agreement Name of agency(ies) implementing the project Name of the contract as well as indicate procurement guidelines used, e.g., RA 9184 IRR, WB, ADB or JICA procurement guidelines Details on the contract to be procured, by component, by package Date when tendering process and/or advertisement started (mm/dd/yyyy) Date when bid documents containing the technical and financial proposals were submitted by the pre-qualified contractors and when bids were opened by the implementing agency (mm/dd/yyyy) Date when evaluation of technical and financial proposals of short-listed consulting firms or pre-qualified contractors were completed (mm/dd/yyyy) Date when contract with consulting firm or contractor was awarded or approved and signed by the head of the implementing agency (mm/dd/yyyy) Date when NTP was issued by the implementing agency to the winning bidder (mm/dd/yyyy) Number of months it took an implementing agency to complete the bidding process, i.e., from start of tendering process/advertisement to NTP issuance Number of months it took an implementing agency to secure the concurrence or approval of the funding institution, i.e., from start of tendering to contract award Actual number of months it took the implementing agency to process the contract |
| --- | --- |

Note:  In accordance with RA 9184 or the Procurement Reform Act (PRA), the procurement process, from opening of bids to award of contract, should not exceed three (3) months (Section 38 of the PRA).

CY 2012 ODA PORTFOLIO REVIEW

Table 9B

Funds Flow Timelines

(Withdrawal applications covering loan proceeds deposited in project accounts in CY 2012)

GFI Name

As of December 31, 2012

| Project Title Implementing Agency Fund Source Withdrawal Application No. __ WA Amount Requested (US$ M) WA Applied (Date Received by FS) WA Release (Date Received by BTr) WA Application to Release (No. of Days) BTr Notice Date (Date Received by IA) WA Release to BTr Notice (No. of Days) Application for NCA (Date Received by DBM) NCA Release (Date Received by IA) BTr Notice to NCA Release (No. of Days) Total Processing Time from WA to NCA Release (No. of Days) | As indicated in loan agreement Name of agency(ies) implementing the project Name of funding institution where loan proceeds was sourced Withdrawal application indicating the number (1 being the first application since project start and succeeding numbers for subsequent applications) The amount of loan proceeds requested in the withdrawal application, in US$ M Date when funding source received the withdrawal application (mm/dd/yyyy) Date when Bureau of Treasury received notice of release by the funding source of loan proceeds to the Philippine government (mm/dd/yyyy) Number of days from date when funding source received the withdrawal application (column 1) to date when Bureau of Treasure received notice of release of loan proceeds (column 2) Date when implementing agency received the notice from the Bureau of Treasury (mm/dd/yyyy) Number of days from date when BTr received notice of release (column 2) to date when agency received BTr notice (column 4) Date when Department of Budget and Management received the request for NCA from the implementing agency (mm/dd/yyyy) Date when implementing agency received release of NCA from DBM (mm/dd/yyyy) Number of days from date when IA received BTr notice (column 4) to date when date when IA received NCA release (column 7) Sum of number of days in column 3 (withdrawal application), column 5 (BTr notice) and column 8 (NCA processing) |
| --- | --- |