## 3-N
Annex 3-N
CY 2013 ODA Portfolio Review Physical Accomplishments as of CY 2013
Loan ID |  | Loan Title | IA | FI | Loan Type | Implementation Schedule | Sector | Closing Date | Revised Closing Date |  |  | Physical Accomplishment | [6 empty] | Remarks
[10 empty] | Actual as of Dec 2012 % | Actual as of Dec 2013 % | Target (%) | Actual (%) | Slippage | Time Elapsed (%) | Physical Status as of 2013 | Physical Status as of 2012 | Performance
Based on Original Implementation Schedule
1 | 767-PH | Rapid Food Production Enhancement Programme | DA | IFAD | Program | 1 | AARNR | 2017-06-30 |  | 89 | 95 | 9 | 6 | -3 | 54.23 | Behind Schedule | Behind Schedule | Same |  | Same Behind | 27
2 | PH-P251 | Mindanao Sustainable Agrarian and Agriculture Development Project (MINSAAD) | DAR | JICA | Project | 1 | AARNR | 2019-07-03 |  |  |  | - | 5.15 | - | 21.36 | Behind Schedule | Newly Effective | Worse |  | Same On Sched | 3
3 | PH-P242 | Agrarian Reform Infrastructure Support Project III (ARISPIII) | DAR | JICA | Project | 1 | AARNR | 2017-04-15 |  |  |  | 93.17 | 87.96 | -5.21 | 63.46 | Behind Schedule | Ahead of Schedule | Worse |  | Same Ahead | 1
4 | Italy-1 | Italian Assistance to the Agrarian Reform Community Development Support Program (IARCDSP) | DAR | Italy | Project | 1 | AARNR | 2019-04-11 |  |  |  | - | - | - | 16.03 | On Schedule | Newly Signed | Same |  | Behind - On Sched | 3 | good
5 | 2515-PHI | Credit for Better Health Care Project | DBP | ADB | Project | 1 | SRCD | 2015-08-19 |  |  |  | 36 | 23 | -13 | 72.8 | Behind Schedule | Behind Schedule | Same |  | On Sched - Behind | 5 | bad
6 | PH-P245 | Logistics Infrastructure Development Project | DBP | JICA | Project | 1 | INFRA | 2016-12-24 |  |  |  | 6 | 3 | -3 | 57.41 | Behind Schedule | On Schedule | Worse |  | NE - On Sched | 3 | good
7 | PH-P243 | Environmental Development Project | DBP | JICA | Project | 1 | INFRA | 2016-01-07 |  |  |  | 20 | 11 | -9 | 71.17 | Behind Schedule | On Schedule | Worse |  | NE - Behind | 8 | bad
8 | PH-8119 | Regional Infrastructure for Growth Project | DBP | WB | Project | 1 | INFRA | 2016-11-30 |  |  |  | 6 | 0 | -6 | 29.52 | Behind Schedule | Newly Effective | Worse |  | New | 10
9 | 2957-PHI | Integrated Natural Resources and Environmental Management Project | DENR | ADB | Project | 1 | AARNR | 2020-12-31 |  |  |  | - | - | - | 5.33 | On Schedule | - | Same |  | PC | 7
| I-890-PH |  |  | IFAD | Project | 1 |  | 2020-12-31 |  |  |  | - | - | - | 5.33 |  |  |  |  | Ahead - On Sched | 1
10 | KfW-02 | Community Based Forest and Mangrove Management Project | DENR | Germany | Project | 1 | AARNR | 2016-01-13 |  |  |  | 81.84 | 78 | -3.84 | 66.1 | Behind Schedule | Behind Schedule | Same |  | On Sched - Ahead | 2
11 | PH-P248 | Forestland Management Project | DENR | JICA | Project | 1 | AARNR | 2022-07-03 |  |  |  | - | - | - | 14.95 | Behind Schedule | Newly Effective | Worse |  |  | 70
12 | Austria-7 | Bureau of Fire Protection Capability Building Program for Selected Priority Cities Project | DILG | Austria | Project | 1 | GID | 2014-04-05 |  |  |  | 100 | 99 | -1 | 86.99 | On Schedule | Ahead of Schedule | Same
13 | 2964-PHI | Market Transformation Thru Introduction of Energy Efficient Electric Vehicles Project | DOE | ADB | Project | 1 | INFRA | 2018-06-30 |  |  |  | - | - | - | 1.08 | On Schedule | - | Same
| 8216-PHI |  |  | CTF |  | 1 |  | 2018-06-30 |  |  |  | - | - | - | 1.08
14 | PH-C24 | Development Policy Support Program-Investment Climate | DOF | JICA | Program | 1 | ITT | 2015-12-17 |  |  |  | - | - | - | 34.61 | On Schedule | Newly Effective | Better
15 | 8238-PH | Second Development Policy Loan to Foster More Inclusive Growth: Supplemental Financing for Post Typhoon Recovery | DOF | WB | Program | 1 | GID | 2014-12-31 |  |  |  | - | - | - | - | Newly Signed | - | Same
16 | 8328-PH | Second Development Policy Loan to Foster More Inclusive Growth: Supplemental Financing for Post Typhoon Recovery | DOF | WB |  |  | GID |  |  |  |  | - | - | - | - | Physically Completed | - | Same
17 | 3080-PHI | Emergency Assistance for Relief and Recovery from Typhoon Yolanda | DOF | ADB | [7 empty] | - | - | - | - | Newly Signed | - | -
18 | FRANCE-3 | Greater Modular Access (GMA) RoRo Ports | DOTC | France | Project | 1 | INFRA | 2012-11-23 |  |  |  | - | - | - | 136.05 | Behind Schedule | Behind Schedule | Same
19 | PH-P255 | Capacity Enhancement of Mass Transit Systems in Metro Manila | DOTC | JICA | Project | 1 | INFRA | 2020-11-22 |  |  |  | - | - | - | 1.53 | On Schedule | - | Same
20 | PH-P257 | Maritime Safety Capability Improvement Project for the Philippine Coast Guard | DOTC | JICA | Project | 1 | INFRA |  |  |  |  | - | - | - | - | Newly Signed | - | -
21 | PH-P256 | New Bohol Airport Construction and Sustainable Environment Protection Project | DOTC | JICA | Project | 1 | INFRA | 2020-07-24 |  |  |  | - | - | - | 6.26 | On Schedule | - | Same
22 | PHL-11 | Puerto Princesa Airport Development Project | DOTC | Korea | Project | 1 | INFRA | 2017-06-21 |  |  |  | - | - | - | 22.82 | On Schedule | Newly Effective | Better | Procurement stage.
23 | PHL-13 | Laguindingan Airport Air-Navigation System and Support Facilities Supply Project | DOTC | Korea | Project | 1 | INFRA | 2014-07-10 |  |  |  | 68 | 30.7 | -37.3 | 78.32 | Behind Schedule | Behind Schedule | Same
24 | PH-P246 | Post Ondoy and Pepeng Short-term Infrastructure Rehabilitation Project | DPWH | JICA | Project | 1 | INFRA | 2013-09-21 |  |  |  | 100 | 100 | 0 | 109.22 | On Schedule | Behind Schedule | Better
25 | PH-P249 | Central Luzon Link Expressway Project | DPWH | JICA | Project | 1 | INFRA | 2019-07-03 |  |  |  | - | - | - | 21.36 | On Schedule | Newly Effective | Better | Procurement of civil works ongoing
26 | PH-P253 | Flood Risk Management Project in Cagayan River, Tagoloan River, and Imus River | DPWH | JICA | Project | 1 | INFRA | 2020-07-03 |  |  |  | - | - | - | 18.69 | Behind Schedule | Newly Effective | Worse | DED commenced in December 2013.
27 | PH-P252 | Pasig-Marikina River Channel Improvement Project Phase III | DPWH | JICA | Project | 1 | INFRA | 2019-07-03 |  |  |  | - | - | - | 21.36 | Behind Schedule | Newly Effective | Worse | Project is yet to be started.
28 | PH-P250 | Arterial Road Bypass Project, Phase II (ARBP II) | DPWH | JICA | Project | 1 | INFRA | 2019-07-03 |  |  |  | - | - | - | 21.36 | Behind Schedule | Newly Effective | Worse | Procurement of civil works ongoing
29 | PH-P239 | Pasig Marikina River Channel Improvement Project (Phase II) | DPWH | JICA | Project | 1 | INFRA | 2015-06-21 |  |  |  | 100 | 100 | 0 | 81.62 | Physically Completed | On Schedule | Better | Physically completed in May 2013.
30 | PH-P247 | Road Upgrading and Preservation Project | DPWH | JICA | Project | 1 | INFRA | 2023-07-21 |  |  |  | 7.62 | 7.44 | -0.18 | 20.4 | On Schedule | Behind Schedule | Better
31 | PH-P241 | Pinatubo Hazard Urgent Mitigation Project III | DPWH | JICA | Project | 1 | INFRA | 2015-04-15 |  |  |  | 92.94 | 91.74 | -1.2 | 81.61 | On Schedule | On Schedule | Same
32 | PHL-14 | Samar Pacific Coastal Road Project | DPWH | Korea | Project | 1 | INFRA |  |  |  |  | - | - | - | - | Newly Signed | - | -
33 | PHL-17 | Integrated Disaster Risk Reduction and Climate Change Adaptation Measures in Low Lying Areas of Pampanga | DPWH | Korea |  |  | INFRA |  |  |  |  | - | - | - | - | Newly Signed | - | -
34 | PHL-10 | Gapan-San Fernando-Olongapo Road Project, Phase II | DPWH | Korea | Project | 1 | INFRA | 2014-04-20 |  |  |  | 54.35 | 39.75 | -14.6 | 93.3 | Behind Schedule | Behind Schedule | Same | The delay is attribute to the RROW problems and change in design.
35 | 1446P | Road Improvement and Institutional Development Project | DPWH | OFID | Project | 1 | INFRA | 2017-06-30 |  |  |  | - | - | - | 26.9 | Behind Schedule | Newly Effective | Worse
| 2836-PHI |  |  | ADB | Project | 1 |  | 2016-06-30 |  |  |  | - | - | - | 36.71
36 | 2662-PHI | Social Protection Support Project | DSWD | ADB | Program | 1 | SRCD | 2016-03-31 | [6 empty] | 56.9 | Behind Schedule | Behind Schedule | Same
37 | PH-7805 | Social Welfare and Development Reform | DSWD | WB | Program | 1 | SRCD | 2014-06-30 |  |  |  | - | - | - | 88.63 | On Schedule | On Schedule | Better
| PH-8218 | Social Welfare and Development Reform Project (Additional Financing) |  |  | Program | 1 |  | 2015-12-31 |  |  |  | - | - | - | 24.97
38 | PH-7959 | KALAHI-CIDSS Project (Additional Financing) | DSWD | WB | Project | 1 | SRCD | 2014-05-14 |  |  |  | - | - | - | 88.6 | On Schedule | On Schedule | Same
39 | IFAD-661-PH | Rural Micro-Enterprise Promotion Programme | DTI | IFAD | Project | 1 | ITT | 2014-06-30 |  |  |  | 100 | 100 | 0 | 93.53 | Physically Completed | Ahead of Schedule | Better
40 | PH-P244 | Agriculture Credit Support Project | LBP | JICA | Project | 1 | AARNR | 2017-03-23 |  |  |  | - | - | - | 53.93 | On Schedule | On Schedule | Same
41 | 8162-PH | Metro Manila Wastewater Management Project | LBP | WB | Project | 1 | INFRA | 2017-06-30 |  |  |  | 6 | 0.65 | -5.35 | 25.54 | Behind Schedule | Newly Effective | Worse
42 | PH-8035 | Laguna de Bay Institutional Strengthening and Community Participation Project (LISCOP) - Additional Financing | LLDA | WB | Project | 1 | AARNR | 2014-04-30 |  |  |  | - | - | - | 88.1 | Behind Schedule | Behind Schedule | Same
43 | CHI-7 | Angat Water Utilization and Aqueduct Improvement Project (AWUAIP)-Phase II | MWSS | China | Project | 1 | AARNR | 2014-05-07 |  |  |  | 100 | 100 | 0 | 91.31 | Ahead of Schedule | Ahead of Schedule | Same
44 | CHI-6 | Agno River Integrated Irrigation Project | NIA | China | Project | 1 | AARNR | 2013-12-31 |  |  |  | 100 | 100 | 0 | 100 | Physically Completed | On Schedule | Better
45 | PH-P254 | National Irrigation Sector Rehabilitation and Improvement Project (NISRIP) | NIA | JICA | Project | 1 | AARNR | 2019-07-03 |  |  |  | 11.56 | 1.45 | -10.11 | 21.36 | Behind Schedule | Behind Schedule | Same | Start-up stage
46 | PHL-15 | Jalaur River Multipurpose Irrigation Project, Phase II | NIA | Korea | Project | 1 | AARNR | 2018-05-28 |  |  |  | 15.38 | 5.49 | -9.89 | 19.83 | Behind Schedule | Behind Schedule | Same | Start-up stage
47 | PH-7709 | Participatory Irrigation Development Project | NIA | WB | Project | 1 | AARNR | 2015-03-31 |  |  |  | 67.51 | 48.75 | -18.76 | 76.95 | Behind Schedule | Behind Schedule | Same
Based on Revised Implementation Schedule
48 | PH-79120 | ARMM Social Fund (Additional Financing) | ARG | WB | Project | 2 | SRCD | 2013-05-31 | 2014-05-31 |  |  | - | 88.03 | - | 88.41 | On Schedule | Behind Schedule | Better
49 | PH-7431 | National Program Support for Tax Administration | BIR | WB | Program | 2 | GID | 2011-12-31 | 2013-06-30 |  |  |  |  | 0 | 108.38 | Behind Schedule | Behind Schedule | Same
50 | PH-7440 | Mindanao Rural Development Project-Phase 2 | DA | WB | Project | 1 | AARNR | 2012-12-31 | 2014-12-31 | 64.03 | 83.23 | 20.66 | 19.2 | -1.46 | 86.67 | Behind Schedule | Behind Schedule | Same
51 | 749-PH | Second Cordillera Highland Agricultural Resource Management Project | DA | IFAD | Project | 2 | AARNR | 2016-06-30 |  | 57.3 | 73.02 | 78.22 | 73.02 | -5.2 | 67.25 | Behind Schedule | Behind Schedule | Same
| 1224P |  |  | OFID | Project | 2 |  | 2013-07-31 | 2014-07-31 | [5 empty] | 89.42
52 | FRANCE-2 | Tulay ng Pangulo Para sa Kaunlarang Pang-agraryo Project | DAR | France | Project | 1 | INFRA | 2013-02-19 | 2014-02-19 | [5 empty] | 97.26 | Behind Schedule | Behind Schedule | Same
53 | 2465-PHI | Agrarian Reform Communities Project II (ARCPII) | DAR | ADB | Project | 1 | AARNR | 2015-06-30 |  |  |  | 84.7 | 63.55 | -21.15 | 76.35 | Behind Schedule | Behind Schedule | Same
| 1225P |  |  | OFID | Project | 2 |  | 2013-12-31 | 2014-12-31 | [5 empty] | 82.85
54 | 2311-PHI | Integrated Coastal Resources Management Project | DENR | ADB | Project | 2 | AARNR | 2013-06-30 | 2014-06-30 |  |  | 100 | 82.2 | -17.8 | 92.92 | Behind Schedule | Behind Schedule | Same
55 | PH-7470 | National Program Support for Environment and Natural Resources Management Project | DENR | WB | Program | 2 | AARNR | 2012-12-31 | 2013-12-31 |  |  | 100 | 91.43 | -8.57 | 100 | Behind Schedule | Behind Schedule | Same | Uncompleted activities to be undertaken using DENR local funds.
56 | PH-7298 | Land Administration & Management Project Phase II | DENR | WB | Project | 2 | AARNR | 2011-03-31 | 2014-03-30 |  |  | 100 | 100 | 0 | 97.12 | Physically Completed | On Schedule | Better
57 | 2507-PHI | Philippine Energy Efficiency Project | DOE | ADB | Project | 2 | INFRA | 2011-10-31 | 2013-12-31 |  |  | 100 | 100 | 0 | 100 | Physically Completed | Behind Schedule | Better
58 | 2137-PHI | Health Sector Development Project | DOH | ADB | Project | 2 | SRCD | 2011-12-31 | 2013-05-16 |  |  | 100 | 99 | -1 | 107.52 | Physically Completed | Physically Completed | Same
59 | A-200665109 | Health Sector Reform Project | DOH | Germany | Project | 2 | SRCD | 2011-12-31 | 2014-12-31 |  |  | 80 | 75 | -5 | 84.65 | Behind Schedule | Behind Schedule | Same
60 | PH-7290 | Second Women's Health and Safe Motherhood Project | DOH | WB | Project | 2 | SRCD | 2012-06-30 | 2013-06-30 |  |  | 100 | 87 | -13 | 106.71 | Behind Schedule | Behind Schedule | Same
61 | PH-P228 | New Communications, Navigation and Surveillance/Air Traffic Management Systems Development | DOTC | JICA | Project | 2 | INFRA | 2010-02-21 | 2017-05-21 |  |  | - | 31.4 | - | 76.23 | Behind Schedule | Behind Schedule | Same | Works resumed in 2013 after contract suspension in 2011.
62 | PHL-5 | Laguindingan Airport Development Project | DOTC | Korea | Project | 2 | INFRA | 2002-06-19 | 2014-10-25 |  |  | 100 | 100 | 0 | 95.01 | Physically Completed | Behind Schedule | Better
63 | FRANCE-1 | Mega Bridges for Urban and Rural Development | DPWH | France | Project | 2 | INFRA | 2012-09-29 | 2013-09-29 |  |  | 56.61 | 55.83 | -0.78 | 105.18 | Ahead of Schedule | On Schedule | Same | Loan closed but works still ongoing.
64 | PHL-9 | Bacolod-Silay Airport Access Road Project | DPWH | Korea | Project | 2 | INFRA | 2013-06-20 | 2014-03-31 |  |  | 100 | 100 | 0 | 114.49 | Physically Completed | Behind Schedule | Better | Civil works 100 percent complete but processing and payments of eligible expenses ongoing.
65 | SAUDI-1/433 | Mindanao Roads Improvement Project | DPWH | KSA | Project | 2 | INFRA | 2009-12-31 | 2014-10-11 |  |  | 36.01 | 33.64 | -2.37 | 206.72 | Behind Schedule | Behind Schedule | Same
66 | Spain-8 | Bridge Construction/Replacement Project | DPWH | Spain | Project | 2 | INFRA | 2013-06-10 | 2013-11-27 |  |  | 64.66 | 57.46 | -7.2 |  | Behind Schedule | On Schedule | Worse
67 | PH-75520 | National Road Improvement Management Project Phase II | DPWH | WB | Project | 2 | INFRA | 2012-12-31 | 2014-12-31 |  |  | - | - | - | 126.94 | Behind Schedule | Behind Schedule | Same
68 | AI-200165951 | Credit Line for Energy Efficiency and Climate Protection in the Philippines (CLEECP) | LBP | Germany | Project | 2 | INFRA | 2012-12-31 | 2013-12-31 |  |  | - | - | - | 100 | Behind Schedule | Behind Schedule | Same
69 | PH-4833 | Support for Strategic Local Development and Investment Project | LBP | WB | Project | 2 | INFRA | 2012-06-30 | 2014-02-28 |  |  | - | - | - | 97.69 | Behind Schedule | On Schedule | Worse
70 | 200665240 | Provincial Towns Water Supply Programme III | LWUA | Germany | Project | 2 | INFRA | 2013-12-31 | 2015-12-31 |  |  | - | - | - | 58.02 | Behind Schedule | Behind Schedule | Same
71 | PH-P221 | Help for Catubig Agricultural Advancement Project Stage I | NIA | JICA | Project | 2 | AARNR | 2011-01-23 | 2013-01-23 |  |  | 100 | 97.01 | -2.99 | 108.51 | Behind Schedule | Behind Schedule | Same
*The review covers 77 ODA loans supporting 71 projects.