## 3-R
ANNEX 3-R
CY 2013 ODA Portfolio Review
Actual Problem Projects in CY 2013
Project Title | DP | IA | NET COMM. (US$M) | SCHED. AVAILMENT (US$M) | ACTUAL AVAILMENT (US$M) | BACKLOG AMOUNT (US$M) | INDICATORS BREACHED
Alert Level II (Critical Stage)
1. Credit Line for Energy Efficiency and Climate Protection in the Philippines | Germany | LBP | 26.43 | 25.17 | 0.04 | 25.13 | 1a, 1b, 2a, 2b, 4a
2. Integrated Coastal Resources Management Project | ADB | DENR | 33.8 | 25.72 | 18.28 | 7.44 | 1a, 1b, 2a, 2b
3. New Communications, Navigation and Surveillance/Air Traffic Management Systems Development | JICA | DOTC | 219.76 | 67.52 | 36.81 | 30.71 | 1b, 2a, 2b
4. Agrarian Reform Communities Project II | OFID | DAR | 30 | 15.58 | 3.26 | 12.32 | 1a, 1b, 2a, 2b
| ADB |  | 70 | 53.45 | 12.82 | 40.63
5. Second Cordillera Highland Agricultural Resource Management Project | OFID | DA | 10 | 8.93 | 1.21 | 7.72 | 1a, 1b, 2a, 2b
| IFAD |  | 26.6 | 17.38 | 5.69 | 11.69
6. Provincial Towns Water Supply Programme III | Germany | LWUA | 13.61 | 10.29 | 1.02 | 9.27 | 1a, 1b, 2a, 2b, 4b
7. National Program Support for Tax Administration | WB | BIR | 11 | 6.75 | 6.75 | 0 | 1b, 4a
8. Participatory Irrigation Development Project | WB | NIA | 70.36 | 51 | 26.14 | 24.86 | 1a, 1b, 2a, 2b
9. Tulay ng Pangulo para sa Kaunlarang Pang-agraryo Project | France | DAR | 299.52 | 254.86 | 248.35 | 6.51
10. Help for Catubig Agricultural Advancement Project Stage I | JICA | NIA | 42.98 | 42.98 | 42.98 | 0 | 4a
11. Greater Maritime Access Modular Roro POrts | France | DOTC | 342.7 | 342.7 | 85.7 | 256.99
12. National Road Improvement Management Project Phase II | WB | DPWH | 232 | 139.29 | 80.39 | 58.9 | 1a, 1b, 2b
13. Health Sector Reform Project | Germany | DOH | 13.21 | 8.72 | 9.18 | 0.46 | 1a, 2a
14. Mega Bridges for Urban and Rural Developmen | France | DPWH | 176.13 | 176.13 | 176.13 | 0 | 1a, 4a
Subtotal Level II |  |  | 1618.1 | 1246.47 | 754.75 | 492.63
Alert Level I (Early Warning Stage)
15. Laguindingan Airport Air-Navigation System and Support Facilities Supply | South Korea | DOTC | 13.29 | 9.58 | 0.79 | 8.79 | 1b, 2a, 2b, 4a
16. Road Improvement and Institution Development | ADB | DPWH | 62 | 15.5 | 1.89 | 13.61 | 1a, 1b, 2a, 2b
| OFID | DPWH | 30 | 0.3 | 0 | 0.3
17. Second Women’s Health and Safe Motherhood Project | WB | DOH | 16 | 16 | 11.7 | 4.31 | 1b, 4a
Subtotal Level I |  |  | 121.29 | 41.38 | 14.38 | 27.01
TOTAL |  |  | 1739.39 | 1292.1 | 768.54 | 519.64