## 5-B
Annex 5-B
CY 2013 ODA Portfolio Review
Results from Ex-Post Evaluations
Project | Description | Actual Cost | Rating | Output | Outcome
1.) Metro Cebu Development Project III | The project involved the reclamation and development of new land for an industrial zone and construction of a coastal road to attract enterprises and facilitate smooth traffic flow in Metro Cebu. | ¥ 37,655 M/ PhP84,347 M Exchange Rate: 1PhP= ¥1.85-2.24 | D Unsatisfactory | Construction of Cebu South Coastal Road (totalling 7.75km) Causeway Section Segment 2): construction of a 6-lane 4.02km highway and a 4-lane 0.84 km highway with a total length of 4.86 km Central Business District Section (Segment 3): construction of a 4-lane 2.89 km highway including the viaduct section with a total length of 1.62km Segment 3 was divided into 3A (viaduct section), 3B1 (approach section), and 3B2 (tunnel section), procurement of works was made by 3 packages. Development of resettlement sites | A survey was administered in January 2013 to 201 residents along the project road as well as road users. Results of the survey show that: (1) among the respondents, 79 percent answered that there was an improvement in traffic congestion along the project area (2) about 70 percent answered that the travel time was shortened. The actual travel time using the South Coastal road (project road) was shortened by 14 minutes. (3) respondents conceive that the accessibility to each facility was improved: Markets, shops, trade centers – 61% Social services – 45% Hospitals – 21% Government offices – 10% Cebu Port – 94% Mactan Airport – 58% (4) about 80 percent of the respondents answered that highway safety was improved (5) about 45 percent of the respondents answered that there was an increase in household income
2.) 2nd Mandaue-Mactan Bridge and Metro Cebu Road Project | The project involved the construction of the Second Mactan Bridge connecting Cebu and Mactan Island to improve traffic safety and efficiency between the two islands, and construction of the Talisay section of the coastal road to alleviate traffic congestion in central Metro Cebu. | ¥ 15,647 M/ PhP40,995 M Exchange Rate: 1PhP=¥ 2.62 | C Partially Satisfactory | Second Mactan Bridge (main bridge length: 410m, 4 lanes) : Approach Road (total length: 3,292m: viaduct 635m, approach road 2,657m) Flyover for left turn traffic 192m: (additional work) | Since only the vehicles with less than 6 wheels are allowed to pass the First Mactan Bridge, large vehicles pass Second Mactan Bridge only. This results in segregation of passable route by type of vehicle, and it has contributed to enhancement of logistics efficiency between Cebu city and Mactan Island because of increase of efficiency of transport (however, only during the period when the total traffic volume of both bridges is much less than the highway capacity). Since the highway capacity was increased because of the completion of Second Mactan Bridge and Cebu South Coastal Road, the project contributed to improvement of traffic condition in the central urban area of Cebu. The access from the Cebu southern district (Naga) to Mactan Island (Mactan International Airport, Economic Zones I and II, and resort areas in the east coast are located) was improved by diverting the central Cebu city and passing First and Second Mactan bridges, the travel time was shortened (by about 15 minutes in average).
3.) Agno River Flood Control Project II and II-B | The project involved the construction of diversion and floodway structures, and repair and construction of dikes and bridges in the middle section of the Agno River to reduce flood damages in the Agno River drainage basin. | ¥ 13,041 M/ PhP29,994 M Exchange Rate: 1PhP＝¥ 2.3 (Average between Jan. 1998 to Nov. 2009) | B Satisfactory | Bayambang Stretch Improvement Guide Channel to Bayambang Stretch Social Development for the Poponto Swamp (including construction of Evacuation Mound Centers) Hector Mendoza Bridge | A beneficiary survey was conducted in three municipalities in the project area, Bayambang, Bautista and Alcala, consisting of 116 barangays. Ten barangays were randomly selected from each municipalities followed by a random selection of six households from each barangay, totalling to 60 households. Survey and interviews with the beneficiaries showed that: (1) no flood damage (e.g., death, missing persons, persons affected, damage to properties, infrastructure facilities, and agricultural production) has occurred after project completion. According to the beneficiary survey, over 95% of respondents answered “no damage” or “small damage” after the project completion. (2) More than 95% of respondents answered that all the items including overall living environment, overall safety situation during flood, health and sanitation situation were “highly improved” or “improved” (3) all the respondents answered the situation has “highly improved” or “improved.” (4) The households interviewed during the field survey pointed out that their income increased by PhP40,000.
4.) 2nd Magsaysay Bridge and Butuan City Bypass Road | The project involved the construction of a new bridge and a bypass road at the crossing point of the Agusan River on the Butuan-Cagayan de Oro-Iligan Road to alleviate traffic congestions in Butuan City and to facilitate smooth traffic and transportation between major cities in northeast Mindanao. | ¥ 5,722 M PhP12,875 M Exchange Rate: 1PhP=¥2.25 (Average between August 2000 and December 2008) | B Satisfactory | Steel cable-stayed bridge: Length 360m, 2 lanes Approach bridge: Steel girder bridge 548m Bypass road: Length 9,430m (construction of bypass road 8,100m + rehabilitation of Maguinda Las Nieves Road 1,330m), 2 lanes | Travel time was measured by the Evaluator for both the old and new bridge routes in January 2013. Actual measurement revealed the following: (1) Reduced travel time from 30 minutes to 16.5 minutes (old bridge) to 13 minutes (new bridge) (2) Improved average velocity of vehicles from 20 km/hr to 35 km/hr (old bridge) and 60 km/hr (new bridge) A beneficiary survey was conducted with 101 participants who are residents and transport companies located near the old and new bridges. Results of the survey showed that: (1) about 81 percent answered that there was a reduction in the number of traffic accidents (2) about 95 percent responded that traffic congestion around the old bridge improved (3) about 81 percent replied that travel time was shortened (4) 42 of the 101 respondents answered that there was a reduction in travel cost (5) about 80 percent conceive that accessibility to key places (shops, markets, schools, hospitals and offices) improved
5.) Laoag Flood Control and Sabo Project | The project involved the construction of Sabo dams, repair and construction of dikes and spur dikes in the Laoag River to reduce flood damages in the project area. | ¥10,591 M/ PhP23,300 M Exchange Rate: 1PhP＝¥2.2 (Average between Sept. 2001 to Dec. 2008) | B Satisfactory | Sabo Dam Works (5 dams) ・Sediment capacity: 4,709,000m3 Laoag-Bongo River Improvement Works - Improvement Length: 14.0 km - Earth Dike: 12,500 m - Riverwall: 1,100 m - Spur Dike: 6 units - Sluiceway: 10 units 3) Alluvial Fan River Improvement Works ・Improvement Length:39km - Earth Dike:70,400 m - Spur Dike:1,036 m - Groundsill: 4 units - Sluiceway: 15 units - Existing Bridge Extension:1 | A beneficiary survey was conducted in Laoag City and ten municipalities in the project area (San Nicolas, Piddig, Sarrat, Banna, Dingras, Marcos, Nueva Era, Solsona, Carasi and Vintar) consisting of 284 barangays. Ten barangays were randomly selected, followed by a random selection of six households from each barangay, totalling to 60 households. Results of the survey show the following outcomes: (1) no inundation of access roads to the Laoag Airport and to the Gilbert Bridge during times of typhoons and monsoon rainfalls; (2) improved access to schools even during times of typhoons (3) reduced flood damages by typhoons and monsoon rainfalls
6.) Bohol Irrigation Project Phase 2 | The project involved agricultural development through construction of a dam, main, lateral and drainage canals, and levelling work and main farm development to increase rice production. | ¥7,653 million Exchange Rate: 1Php=¥2.21 (Average over project period) | B Satisfactory | - Construction of Bayongan Dam: Zone earthfill type, active storage capacity 25.1MCM, dam height 35.5m, catchment area 11.2k m2 - Main canals: 17.76km (Bayongan area) - Lateral canals: 42.40km (Bayongan System) - Lateral canals: 15.82km (Cayapas System) - Drainage canal: 66.91km - Construction of main farm ditches and land levelling work: 1,479ha | Average actual gross farm income improved from PhP3,347 per hectare at project appraisal (1999) to PhP25.427 per hectare at project completion (2012). Actual yield of rice per hectare increased from 2.99 metric tons/ha at project appraisal to 4.38 metric tons/ha during wet season and 4.9 metric tons/ha during dry season at project completion. A beneficiary survey was conducted for 100 farmers: 53 farmers who are residing in the area near the main and lateral canals and 47 farmers near the tertiary canals. Almost 80 percent of the farmer beneficiaries responded that their living conditions improved along with the increase in income: - Improved dietary choices (can buy variety of food not previously affordable) - Better housing (either new or newly-renovated/expanded) - Better access to education for children - Investment opportunities/businesses - Purchase of vehicles
7.) Subic- Clark-Tarlac Expressway Project | The project consisted of the construction of an expressway with a total length of 90 km connecting Subic and Tarlac via Clark to improve transport efficiency, reduce transport costs and enhance highway safety. | ¥71,734 million Exchange Rate: 1PhP= ¥1.9 - 2.42 (Average between May2002 and July 2008) | B Satisfactory | - divided 4-lane expressway (about 50 km between Subic – Clark)(about 40 km between Clark – Tarlac) - 12 interchanges - 4 long bridges, 33 medium/ small bridges - 12 overbridges - 14 toll stations | A survey was conducted in January 2013 for 403 respondents (road users, travelling on the expressway and residents along the expressway corridor). Results of the survey are the following: (1) approximately 88 percent of the respondents answered that there was substantial improvement in traffic congestion (2) about 90 percent of those surveyed responded that travel time was shortened (3) respondents conceive that accessibility to key facilities improved: Market, shops, trade center – 82 percent Social services – 47 percent Hospitals – 30 percent Government agencies – 35 percent Ports – 34 percent (4) about 60 percent of respondents conceive that the safety on the national road has been improved Actual travel time for the sections between Subic and Clark and between Clark and Tarlac was reduced from 120 minutes and 90 minutes to 35 and 22 minutes, respectively.
8.) LRT Line 1 Capacity Expansion Project II | The project involved the procurement of additional rolling stocks and improvement of signalling system for LRT Line 1. | ¥21,841 million Exchange Rate: 1PhP=¥2.27 (Average between April 2000 and September 2008) | C Partially Satisfactory | Package A (procurement of rolling stocks / civil works): - Procurement of rolling stocks (4 car-train x 12 sets = 48 cars, air-conditioned) - Procurement and installation of signalling system (ATC/ATP/ATO/ATS) - Upgrading of the existing communication system - Procurement of additional equipment for the existing automatic fare collection system (AFCS) - Track-work within depot - Upgrading of power distribution equipment - Civil works (upgrading of stations and depot) - Structural soundness study of Line 1 structures - Replacement and strengthening of walls at 15 stations - Replacement of a roof and walls of the depot Package B (procurement of air conditioners for exiting rolling stocks): - Procurement of air conditioners for existing (first generation) rolling stocks (64 cars) - Renovation of existing rails and sleepers (approximately 4km) - Replacement of faulty air conditioning units of the 2nd generation vehicles - Procurement and installation of equipment for AFCS (automatic gates / ticket machine) delivered by French company - Procurement of equipment and spare parts for track works | A beneficiary survey was conducted in February 2013 for 125 passengers in Blumentritt, Doroteo Jose, EDSA and Monumento stations. Results of the survey show the following outcomes: (1) approximately 70 percent of the beneficiaries replied that the level of comfort in LRT line 1 improved mainly due to air conditioners provided (2) about 80 percent of the respondents answered that infrastructures in stations were improved after project implementation (3) almost 70 percent of the surveyed passengers conceive that the transfers from Line 1 to Lines 2 and 3 are have become more convenient
9) Project for the Improvement of Packaging Technology for Philippine Food Products in the Regions | The project consisted of capacity-building designed to improve and upgrade the packaging technology for food SMEs in the region. | ¥410 million | A Highly Satisfactory | - An integrated database of provided services for Management Information Systems developed - Implementation plan for technology transfer developed - 203 seminars conducted, 47 of which are seminars on basic packaging technology and disseminating specific technologies | - Three technical staffs are able to apply to Philippine food products on High Barrier or Dry/Semi-dry foods technology - Three technical staffs are able to apply to fresh cut vegetables on MAP technology - Three technical staffs are able to apply on developing retort foods using different type of packaging on Retort technology - Five technical staffs are able to design corrugated box with appropriate cushion for fresh fruit transport packaging on Transport Packaging technology Results of the beneficiary survey conducted at the time of the study confirmed that 61 clients from a sample size of 100 had expanded their market (equivalent to 61 percent of the sample). Based on the beneficiary survey, the following outcomes were reported: - roughly 59 percent of clients responded that sales volume increased to 1-200 There are 123 POs outside the pilot sites, and of these, 42 POs (or 34 percent) has adopted and put into practice appropriate technology acquired through the project. - approximately 38 percent of the clients reported a more than 200 percent sales volume increase
10) Project for Enhancement of the Community-Based Forest Management Program (CBFMP) | The project aims to enhance the conservation, rehabilitation and sustainable utilization of forest and land resources within CBFM to contribute to the overall sustainable forest management of the Government of the Philippines. | ¥571 million/ PhP289.85 Million | C Partially Satisfactory | Policy Component One proposal was prepared and submitted to the Joint Coordinating Committee for the following five items: (1) lifting of the ban on logging; (2) land tenure conflicts; (3) conflict resolution for natural resources; (4) renewal of Certificate of Stewardship; and (5) modification of the CBFM Implementation Framework. Training Unit - 17 training workshops including orientation, training needs analysis, CBFM for instructors, participatory rapid appraisal techniques, para-legal, forest fire management, agroforestry, process documents, and practical goat raising - A total of 1,176 people participated in all training conducted during the project period Of this. 462 participated in training on the national level, and 714 within the jurisdiction of the Region 3 Office. The total number of participants for each target group was: 486 from POs, 178 from LGUs, 73 from NGOs, 168 from DENR Provincial Offices, 146 from DENR Municipal Offices, and 125 from the Regional Office. Information Unit - Twelve different information materials were prepared based on the needs identified above, and were distributed to 38 high-priority POs - 1 Training Guide for CBFM Practitioners | The results of the impact survey are as follows. - Of the 60 POs that participated in this project, 82 percent (49 POs) raised their awareness for the CBFM Program, and 72 percent (42 POs) recognized an improvement in the participation of their members. - Of the 11 LGUs that participated in this project, a change for the better in awareness and attitude was observed for staff in nine LGUs. - Of the 28 DENR Provincial/Municipal Office staff, a change in approach to CBFM operations and an improvement in awareness and knowledge about CBFM were observed for 92 percent (26).
11) Mindanao Sustainable Settlement Area Development Project | This project involved development of infrastructure, support for agricultural technology, support for organization of farmers, and strengthening of local barangays to increase farmer’s income and and improve access to infrastructures, such as roads and bridges, barangay health station, and school buildings. | ¥6,872 million Exchange Rate: 1PhP= ¥2.17 (2003-2008 average) | B Satisfactory | Infrastructure Development Farm to Market Road - 354km Farm to Market Bridge – 1,749 km Water Supply System – 39 sites Irrigation Facilities – 2732 ha Barangay Health Station – 96 sites Multi-Purpose Building – 20 sites Postharvest Facility – 111 sites School (Classroom) – 632 rooms Multi-purpose Pavement 91 sites Institutional Development No. of Organizations -1,792 Farmer Para-Technician Trained - 290 persons Farmers Trained - 72,193 persons Training for PMU - 26 sites Training for PMU officers - 4,599 persons Agricultural and Environmental Development Reforestation –10 sites Agro-forestry – 10 sites Fruit-tree – 27 sites Demo Farm - 100 sites Nursery - 10 sites Livestock Development – 59 sites Procurement Equipment Equipment of PMU – 11 sites Equipment of Settlement Management Unit - 16 units School Armchair – 24,750 units Medical Equipment – 94 units O & M Equipment of LGU – 16 sites | According to data extracted from the Assessment of the Level of Development of Agrarian Reform Communities (ALDA),which DAR conducts every year, the average increment in farm households’ Annual average total income in all the areas covered by this project increased from PhP68,148 in 2004, before the implementation of this project, to PhP111,105 in 2009, up by 63 percent, and PhP116,139 in 2011, up by 70 percent. Based from the beneficiary survey, the annual average agricultural income in the four barangays increased by 27 percent over the course of this project. In the simplified beneficiary survey (awareness survey), the following outcomes were generated: (1) approximately 89 percent (93 barangays) of the surveyed barangays perceived that the agricultural income increased after the project. (2) construction of farm to market road increased economic activities -reduction in the transportation cost and time (opportunity cost) -improvement in market access -improvement in access and the rise if a farm price -increase in job opportunities (3) roughly 80 percent of the target barangays where supply systems were constructed in this project answered that water-borne diseases decreased. This decrease in water-borne diseases has led to reduction in medical expenses and improvement in labor productivity.
12.) Bago River Irrigation System Rehabilitation and Improvement Project | The project involved rehabilitation of a weir, main and secondary canals to increase the irrigated area and agricultural production. | ¥3,504 million Exchange Rate: 1PhP=¥2.23 | A Highly satisfactory | Rehabilitation of the existing irrigation system (service area: 12,529 ha) - Rehabilitation of weir accessories - Construction of main canal tunnel: 1,532 m (tunnel was changed to closed conduit) - Rehabilitation of main canals: 29.86 km - Rehabilitation/lining of some secondary canals: 108.77 km - Repair of service roads: 177.78 km Water Management Improvement - Diversion work - Intake structure for terminal canals | Yield for rice increased from 3.2 metric ton per hectare at project appraisal (2002) to 3.7 metric ton per hectare at project completion (2012) during the wet season, while yield during the dry season increased from 2.5 metric tons per hectare to 4.2 metric tons per hectare. Actual gross farm income per hectare per year also increased from PhP41,799 to PhP61,359. Based on a beneficiary survey conducted for 100 farmers residing in the Bago irrigation area, the following outcomes were reported: - Approximately 25 percent of the farmers replied that their rice output increased while 74 percent answered that their rice output largely increased - About 98 percent of the respondents answered that their living standards improved: Improved dietary choices (can buy variety of food not previously affordable) – 73 percent Better housing (either new or newly-renovated/expanded) – 65 percent Better access to education for children – 80 percent Investment opportunities/business – 24 percent Access to variety of entertainment/leisure – 3 percent Purchase of vehicles – 20 percent