## 5D
Annex 5-C
CY 2013 ODA Portfolio Review
Other Evaluation Studies Conducted in 2013
Program/Project | Reported Outputs | Reported Outcomes
IMPLEMENTATION COMPLETION AND RESULTS REPORT
Judicial Reform Support Project | A. Improving case adjudication and access to justice i.Computer-based case management system operating in Supreme Court, Court of Appeals and Court of Tax Appeals. A different system operated in the Sandiganbayan for a while but is now being replaced. Computer-based case management system pilot tested in Pasay City and Lapu-Lapu City Courts. ii.Computer-based records management systems introduced in higher courts iii.Computer-aided transcription equipment not yet installed. iv.High quality study of re-engineering of Court’s jurisdictional structure undertaken and submitted to the Court en Banc, but no action taken. v.Study of options for addressing affordability constraints on access to the courts by the poor completed by 2010 but no action has yet been taken. vi.Eight mobile courts have been established and used to help decongest selected courts and prisons. Two now being used in place of courts damaged by natural disasters. But mobile courts not widely used to extend justice in underserved remote areas. vii.EISP development and adopted in 2009. Additional: •Rules and Procedures for small claims cases improved in 2008 and computer facilities provided to 831 first level courts, helping decongestion. •Judicial Audit in 2010 for Lapu-Lapu City Courts helped to reduce case backlog. | No reported outcomes
B. Enhancing institutional integrity i.Code of Conduct for court and judicial personnel promulgated in 2004 and 97 percent of personnel trained during the project period. ii.Whistle-blower proposal drafts and submitted to Supreme Court but no action yet taken. iii.A computerized judicial performance management system has yet to be implemented in any of the target courts iv.Gender sensitive Human resource Development Plan developed in 2006 and is being implemented. PHILJA has been substantially strengthened with renovation, additional capacity, computer equipment and a distance learning capability.
C. Strengthening institutional capacity i.Regional Office of Court Administrator pilot tested in Lapu-Lapu City but then suspended. No significant decentralization now in place. ii.Financial management improvement program yet to be implemented ii.Pilot Model Halls of Justice completed in Lapu-Lapu City (Visayas) and Angeles City (Luzon) but none in Mindanao. But these are without much of the anticipated systems reforms. iv.E-library established quickly and is widely used thus helping judges and judicial personnel be better informed
D. Assist in strengthening support for the reform process i.No study of the possible impact of APJR reforms has been done. ii.Distinguished lecture series established. Exchanges with numerous foreign judiciaries, including Spain, Egypt, South Africa and China. Asia Pacific Judicial Forum established and held forums in 2006, 2007, 2009 and 2010. iii.Consultations within the judiciary during preparation and in the early years of implementation. Change Management Committee established iv.Wide array of workshops and consultations held early in the project period. Enhanced Justice on Wheels included public information events. First user survey done but second only begun in mid-2013. v.Capacity of Program Management Office weakened, rather than strengthened, during the project period
National Program Support for Basic Education Project |  | The targets for the outputs were exceeded: All high schools considered to be implementing units (i.e. who have FM staff) and all elementary schools and the rest of the high schools (released through the divisions) received the school MOOEs. In an effort to make the MOOE allocation more equitable, in 2012, DepEd implemented an equity-based formula in 2011. At the same time, the DepEd allocation for MOOEs had more than tripled. In 2013 alone, the MOOE allocations have increased from Php 9 billion to Php 12 billion. This was the result of the project having successfully mobilized additional analytical support that showed the importance of MOOE to schools. Beneficiaries indicate that MOOEs are a critical element to ensuring proper functioning of their schools. There are a small number of schools that have indicated they are not collecting their MOOE allocations. To mitigate any potential distribution issues related to MOOE, DepEd is now listing MOOE allocations on its webpage for full transparency. Other indicators show that 76 percent of schools/clusters are eligible to receive school grants, exceeding the target of 65 percent. Furthermore, 88 percent of school heads have been trained in Simplified Accounting Procedures (SAP), and have adequate financial management systems in place, exceeding the 65 percent target. In additional to these achievements, DepEd received technical assistance and financial support from AusAID to develop a Financial Management Information System (FMIS). This system had to be put on hold pending the development of the government wide FMIS.
Rural Power Project |  | At completion, 10 out of 11 participating ECs were financially, as measured by their debt service coverage ratio of greater than one. However attribution to the project is problematic. 20,975 new customers (target 10,000) were provided service, mostly through solar PV, which connected 17,340 households and 2,185 public facilities. In addition,1,450 household connections were provided via mini-grids.
National Sector Support For Health Reform Project | US$49 million worth of public health commodities e.g. drugs, medicines, vaccines provided | Fully Immunized Children (FIC)rate (85% out of 90% target) was not achieved by the final year of the project. The latest FIC rate improved slightly from the baseline, but fell below the target. The data for the FIC were drawn from the Field Health Service Information System (FHSIS). The target TB case detection rate was not achieved by the final year of the project. The latest TB case detection rate is the same as the baseline (72% out of 72% target). The data were drawn from FHSIS. The target 85% TB cure rate was not achieved by the final year of the project. The latest TB cure rate improved very slightly from 82% from the baseline of 81%, but fell behind the target. The data were drawn from the FHSIS.
COMPLETION REPORTS
SECOND CORDILLERA HIGHLAND AGRICULTURAL RESOURCE MANAGEMENT PROJECT/IFAD | Social Mobilization Assisted 381 Pos, of which 14 (56%) are registered, 191 (50%) are profiled, and 180 (47%) have been assessed as to their capability. Provided services to 21,370 individuals in targeted 36,300 households. Community Watershed Conservation and Reforestation 6,210 hectares or 76% of the original target of 8,000 hectares surveyed and awarded to POs. 1,000 hectares out of target 2,170 hectares (46%) planted with seedlings produced by POs. Promotion of Agro-forestry on Slope Areas 509 hectares out of target 2,000 hectares (25%) surveyed. 1,442 completed agro-forestry farmer field school training (59% female). Agriculture, agri-business and income generating activities (4 value chain/enterprise development plans prepared, with 91 validated with stakeholders covering 88 out of 170 barangays. Rural Infrastructure Development 1,318 lineal meters of footpaths constructed and 26.5 hectares of community irrigation scheme rehabilitated
Financial Market Regulation and Intermediation Program-Subprogram 2 |  | Business Constraint Index “access to credit” declined to 17.7 from 31.8. M2/GDP ratio increased to 48.2% from 43% Financial stability index improved from 3.3 to 4.1 Rank of Philippine financial markets improved from 42nd place to 40th place
Local Government Financing and Budget Reform Program Cluster |  | The Bureau of Local Government Finance’s (BLGF) data indicated that cumulative IRAs increased from PhP83.7 billion to PhP108.8 billion between 2007 and 2009. BLGF’s data indicated that LGUs continued to increase spending for key services Data provided by COA showed that the number of fraudulent cases at all sub-national levels have decreased
Support to Philippines Basic Education Reforms (SPHERE) |  | BESR-SPHERE contributed to improvements in learning outcomes as observed in increases in achievement rate from 65% in 2007 to 67% in 2012. It also contributed to improvements in participation rate from 88% in 2007 to 91% in 2012.
MID-TERM EVALUATION
Basic Education Assistance for Muslim Mindanao (BEAM)-ARMM |  | Observable improvements in health seeking behaviors of school children and in health conditions of schools which led to reduced absenteeism and improved performance of pupils.
Social Protection Initiative Support to DSWD’s Technical Assistance Facility |  | Technical Assistance Facility (TAF) as a model/mechanism for harmonising donor support to Social Protection continues to be relevant and useful to DSWD. The mechanism avoided duplication of technical assistance and led to work harmonisation among donor agencies on SP.
Philippines Australia Human Resource and Organizational Development Facility (PAHRODF) |  | Australian Government “can be very satisfied with its implementation...and be prepared to acknowledge that the Facility represents a successful program, of which some aspects are transferable to other AusAID [sic] programs elsewhere.” HRODF outcomes are making governance reforms occur at a faster pace.
END-OF-PROJECT EVALUATION
GREAT Women Project (GWP) |  | Succeeded in developing and testing an approach to WEE; this convergence approach and a focus on women’s rights and gender equality have been found to be effective in creating an enabling environment for WEE at national and local levels, with more effectiveness observed at local ( LGU) level.
Succeeded in increasing PCW’s visibility in government, in creating a concrete image of its role as a resource for capacity development on gender mainstreaming and women’s economic empowerment.
Instrumental in NGAs and LGUs learning how to apply ‘gender mainstreaming’ in their policy-making, planning and budgeting, and service delivery, improving their effectiveness as government agencies and institutions as their services benefitted local constituents. The latter is the strongest basis for concluding that gender integration in all aspects of government agency functions contribute to good governance.