## 3K2 (hidden)
Annex 3-F
CY 2013 ODA Portfolio Review
COMMITMENT FEES PAID IN 2012 AND 2013 BY PROJECT (in US$M)
Project | IA | 2012 | 2013
National Program Support for Tax Administration | BIR | 0.018246 | 0.0128
Mindanao Rural Development Project-Phase 2 | DA | 0.13359 | 0.0343
Infrastructure for Rural Productivity Enhancement Sector | DA | 0.072207
Tulay ng Pangulo Para sa Kaunlarang Pang-agraryo Project | DAR | 2.2383 | 1.3468
Agrarian Reform Communities Project II | DAR | 0.048355
Mindanao Sustainable Agrarian and Agriculture Development Project | DAR | 0.01132 | 0.0585
Agrarian Reform Communities Development Project II | DAR |  | 0.0927
Credit for Better Health Care Project | DBP
Logistics Infrastructure Development Project | DBP
Integrated Coastal Resources Management Project | DENR | 0.094586 | 0.1478
National Program Support for Environment and Natural Resources Management Project | DENR | 0.056535 | 0.0097
Forestland Management Project | DENR | 0.017218 | 0.0916
Community Based Forest and Mangrove Management Project | DENR | 0.0064363 | 0.0045
Land Administration & Management Project Phase II | DENR | 0.0008666
National Support for Basic Education | DepEd | 0.024815 | 0.0018
Mindanao Basic Improvement | DILG |  | 0.018
Philippine Energy Efficiency Project | DOE | 0.019677 | 0.0161
Increasing Computer Television Program I | DOF |  | 0.1268
National Sector Support for Health Reform | DOH | 0.04979
Second Women's Health and Safe Motherhood Project | DOH | 0.022971
Health Sector Development Project | DOH | 0.01695 | 0.004
Greater Maritime Access (GMA) Ports | DOTC | 1.9045 | 0.7178
PH-P256 New Bohol Airport Construction and Sustainable Environment Protection Project | DOTC |  | 0.0172
Laguindingan Airport Development Project | DOTC | 0.039748
Mega Bridges for Urban and Rural Development | DPWH | 0.682 | 0.4772
Road Upgrading and Preservation Project | DPWH | 0.49587 | 0.3959
Road Improvement and Institutional Development Project | DPWH | 0.051667 | 0.0924
Post Ondoy and Pepeng Short-term Infrastructure Rehabilitation Project | DPWH | 0.043913 | 0.012
Central Luzon Link Expressway | DPWH | 0.042562
Pasig Marikina River Channel Improvement Project (Phase II) | DPWH | 0.022099
Flood Risk Management Project along Selected Principal Rivers 2 | DPWH | 0.014089
Arterial Road Bypass Project Phase 2 | DPWH | 0.0085717 | 0.0463
Bridge Construction/Replacement Project | DPWH | 0.0023563 | 0.0001
DPWH Bridge Construction Acceleration Project for Calamity-Stricken Areas | DPWH | 0.00061809
Metro Manila Urban Transport Integration Project | DPWH
PH-P249 Central Luzon Link Expressway Project | DPWH |  | 0.231
PH-P252 Pasig-Marikina River Channel Improvement Project Phase III | DPWH |  | 0.11997
PH-P253 Flood Risk Management Project in Cagayan River, Tagoloan River, and Imus River | DPWH |  | 0.0764
Social Protection Support Project | DSWD | 0.50562 | 0.3652
KALAHI-CIDSS Project | DSWD
2nd Women's Health and Motherhood | IBRD |  | 0.0095
Agriculture Credit Support Project | LBP
ARMM Social Fund for Peace and Development | ASFPD-FMO
Manila Third Sewerage Project | LBP
Support for Strategic Local Development and Investment Project | LBP
Laguna De Bay Institutional Strengthening and Community Participation Project | LLDA | 0.00024258
Development of Poor Urban Communities Sector Project | DBP
Environmental Development Project | DBP
Agno River Integrated Irrigation Project | NIA | 0.14301 | 0.0672
Local Government Financing and Budget Reform Program, Subprogram 2 (LGFBR2) | DOF
National Irrigation Sector Rehabilitation and Improvement Project | NIA | 0.011552 | 0.062
Southern Philippine Irrigation Sector Project | NIA
NorthRail Project Phase 1 Section 1 | NorthRail
Pasig River Dredging Project | PRRC
Judicial Reform Support Project | SC | 0.008108 | 0.0012
Experience of Dual Education and Training | TESDA |  | 0.0161
TOTAL |  | 6.8084 | 4.6568
Note on A8: NEDA: Fin indicators (Net Comm, Sched Avail, Actual Avail, Backlog) are broken down for the two loans, in proportion to their share on the total loan amount (15% & 85%, resp).

## 4-A
Annex 4-A
CY 2014 ODA Portfolio Review
Findings and Recommendations of Supervision Missions
Agency |  | Project | DP | Mission | Date | Rating/Findings | Recommendations/ Remarks
1 | DA | CHARMP2 | OFID | Implementation Support | March | Moderately Satisfactory. The project has made encouraging improvements in its implementation progress and performance, achieving 73% of its overall physical AWPB targets, 58% obligation and 29% disbursement of its overall financial targets. The mission found that most of the key 2013 SIS and the three NEDA/DA/IFAD joint monitoring recommendations have been implemented, though several are still pending. | The primary concerns for the next 3 months include the need to approve and implement the restated project financing agreement to extend the OFID loan. In addition, the project needs to ensure clarity in roles and accountabilities of provincial and municipal structures in a way that strengthens their capability to sustain project outputs and outcomes after the completion of project activities.
2 | DA | RAFPEP | IFAD | Implementation Support | 6 to 13 August | Satisfactory. As of 30 June 2014, IRPEP accomplished a high ratio of its global physical targets and utilized 71.5% of the IFAD loan and 64.8% of GPH funds against a project lapse time of 65%. The mission found that most of the agreed actions of the 2013 MTR and the 2014 IFAD-PH First Quarter Meeting have been implemented, though some of them are still pending. | The project is expected to: (a) complete the IA strengthening activities, especially on O&M of the complete CIS; (b) prepare an exit/sustainability plan for the IAs; (c) turn-over the IA strengthening responsibilities of the institutional development officers and farmer irrigation officers to IA officers and members; (d) follow-up the rehabilitation of CIS damaged by Typhoon Yolanda using RAY programme funds; and (e) make use of the NIA regular funds to close the gaps in the rehabilitated CIS.
3 | DTI | RuMEPP | IFAD | Project Completion Support | 22 June - 4 July | Satisfactory. Although experiencing delays in its first three years of implementation, the program managed to achieve all its physical and financial targets before it officially closed. The outlook for the programs' outcomes are promising, as evidenced by positive results/feedback from ad-hoc outcomes and impact surveys. | Outcomes and impact of the program cannot be comprehensively assessed due to the non-completion of the Impact Study conducted in 2013. Results will be further validated upon the completion of the Impact Study in 2015.