## Table of Contents
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table of Contents
GFI Name
As of December 31, 2015
Project Factsheet
Table 1 | ODA & LFPP | Regional Disaggregation of Projects and Programs
Table 2A | ODA & LFPP | Financial Status of Projects and Programs
Table 2B | ODA & LFPP | Budget Forecast
Table 2C | ODA Only | Loan Disbursement (Withdrawal) Targets
Table 3A | ODA & LFPP | Physical Targets and Actual Accomplishments of Projects and Programs
Table 3B | ODA & LFPP | Components and Physical Outputs of Projects and Programs
Table 3C | ODA & LFPP | Project/Program Component(s) Addressing Climate Change and Contributing to Disaster Risk Reduction
Table 3D | ODA & LFPP | Project(s)/Program(s) with Damaged Output(s), Incomplete Output(s) or Sustainability Issue(s)
Table 4A | ODA & LFPP | Problem Analysis of Projects and Programs
Table 4B | ODA & LFPP | Assumptions and Risk Register
Table 5 | ODA & LFPP | Projects/Programs for Possible Restructuring/ICC Re-evaluation in CY 2016
Table 6 | ODA & LFPP | Project/Program Results
Table 7 | ODA & LFPP | Lessons Learned Register for Projects and Programs

## Table 1
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 1
Regional Disaggregation of Projects and Programs
GFI Name
As of December 31, 2015
PROJECT/PROGRAM TITLE | LOCATION | LATEST APPROVED PROJECT/PROGRAM COST (PhPM)1 |  |  |  | IMPLEMENTATION SCHEDULE |  | REMARKS
| (Region/s) |  |  |  |  | (mm/dd/yyyy)
|  | TP | LP | GP | GPH | Start2 | Completion3
Projects
Project 1 | Total | 105 | 75 | 15 | 15 | 2011-01-01 | 2017-12-31
| Region I | 70 | 50 | 10 | 10 | 2012-01-01 | 2015-12-31
| Region II | 35 | 25 | 5 | 5 | 2012-01-01 | 2015-12-31
| Region N |  |  |  |  | 2013-01-01 | 2014-12-31
Nationwide4
Project-wide5
Unallocated
Project 2 | Total
Region I
Region II
Region N
Nationwide4
Project-wide5
Unallocated
Programs | Total
Program 1 | Region I
Region II
Region N
Nationwide
Nationwide4
Program-wide5
Unallocated
TP - Total Project/Program Cost | LP - Loan Proceeds |  | GP - Grant Proceeds |  | GPH - Local Counterpart Fund
1 For programs/projects funded by off-budget funds, the total approved budget may be used for the total cost of the program/project. In addition, for non-ODA programs, use the total approved budget available for CY 2015 only.
2 Start date refers to the earliest start date among the sub-projects/activities in the region for the project/program.
3 Completion date refers to the latest completion date among the sub-projects/activities in the region for the project/program.
4 Cost known to be incurred in all regions, but breakdown for each region can not be determined.
5. Cost known to be incurred project-or program-wide, but not in all regions, but breakdown per covered region can not be determined.
Projects are defined as special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
Programs are defined as a homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, or for the basic maintenance of the agency’s
administrative operations, or for the provision of staff support to the agency’s administrative operations, or for the provision of staff support to the agency’s line functions.
Prepared by: ______________________________ | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ | Date: _____________________________
(Signature over printed name)

## Table 2A (GFIs)
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 2A
Financial Status of Projects and Programs
GFI Name
As of December 31, 2015
PROJECT/ | FUND | ALLOCATION |  |  |  | OBLIGATIONS |  |  | DISBURSEMENTS
PROGRAM | CATEGORY | As of | CY 2015 |  | Total Available | As of | CY |  | As of | CY
TITLE |  | 31 Dec. 2014 |  |  | To Date | 31 Dec. 20141 | 2015 | Total | 31 Dec. 20142 | 2015 | Total
| (1) | (2) | (3) |  | (6)=(3+4) | (7) | (8) | (9)=(7+8) | (10) | (11) | (12)=(10+11)
Projects
Project 1 | TP
LP
GP
GPH
Project 2 | TP
LP
GP
GPH
Programs
Program 1 | TP
LP
GP
GPH
Program 2 | TP
LP
GP
GPH
TP - Total Project Cost |  | LP - Loan Proceeds |  | GP - Grant Proceeds
1 For locally-funded programs, obligations as of CY 2014 should only include obligations made in CY 2014.
2 For locally-funded programs, disbursements as of CY 2014 should only include disbursements made in CY 2014.
Prepared by: ______________________________ |  |  |  |  | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ |  |  |  |  | Date: _____________________________
(Signature over printed name)

## Table 2B
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 2B
Budget Forecast
GFI Name
As of December 31, 2015
The sum of the multi-year budget requirement and the cumulative obligations as of end 2015 (as per Table 2A) should be equal to the current estimate of the total project cost.
PROJECT/ | FUND | TOTAL COST1 |  |  |  |  | MULTI-YEAR REQUIREMENT FORECAST
PROGRAM | CATEGORY | ICC-Approved |  | L/G | FOA2 | Current | 2016 |  |  |  | 2017 | 2018 | 2019 | 2020 | Future
TITLE |  | Original | Revised | Cost |  | Estimate | 1Q | 2Q | 3Q | 4Q |  |  |  |  | Years
Projects
Project 1 | TP
LP
GP
GPH
Project 2 | TP
LP
GP
GPH
Programs
Program 1 | TP
LP
GP
GPH
Program 2 | TP
LP
GP
GPH
TP - Total Project Cost |  | LP - Loan Proceeds |  | GP - Grant Proceeds
1 For programs/projects funded by off-budget funds, the total approved budget may be used for the total cost of the program/project. In addition, for non-ODA programs, use the total approved budget available for CY 2015 only. | [15 empty] | r
2 FOA - Forward Obligational Authority
Prepared by: ______________________________ | [5 empty] | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ | [5 empty] | Date: _____________________________
(Signature over printed name)

## Table 2C
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 2C
Loan Disbursement (Withdrawal) Targets
GFI Name
As of December 31, 2015
Amounts should be in Original Currency. Amount in the "Total" column should equal to the Net Commitment.
PROJECT/ PROGRAM TITLE | LOAN ORIGINAL CURRENCY | NET COMMITMENT1 (in OC) | DISBURSEMENTS as of Dec 2015 | 2016 TARGETS |  |  |  | FUTURE TARGETS2 |  |  |  | TOTAL | REMARKS3
|  |  |  | Q1 | Q2 | Q3 | Q4 | 2017 | 2018 | 2019 | 2020
| (OC) | (1) | (2) | 2016 TARGETS Q1: (3); FUTURE TARGETS2 2017: (4) | (2+3+4)
Projects
Project 1
Project 2
Project 3
Project N
Programs
Program 1
Program 2
Program 3
1 Loan Amount Less Cancellations
2 Insert additional years as may be necessary
3 Indicate the foreign exchange rate(s) used in setting future targets
Prepared by: ______________________________ |  |  | Date: _______________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: _______________
(Signature over printed name)

## Table 3A
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 3A
Physical Targets and Actual Accomplishments of Projects and Programs
GFI Name
As of December 31, 2015
PROJECT/ PROGRAM TITLE | TARGET (%) |  | ACTUAL (%) |  | FUTURE TARGETS5 | [7 empty] | STATUS AS OF DECEMEBR 2015 (on/ahead/behind schedule, or completed)6 | REMARKS7
| As of 31 Dec. 20141 | For 20152 | As of 31 Dec. 20143 | For 20154 | 2016 |  |  |  | 2017 | 2018 | 2019 | 2020
[5 empty] | 1Q | 2Q | 3Q | 4Q
Projects
Project 1 | 10 | 30 | 11 | 25 | 3 | 2 | 3 | 4 | 12 | 18 | 12 | 10 | On schedule Actual OWPA = 36% Target OWPA = 40%; 10% of target OWPA = 4p.p; On schedule if actual OWPA is between 37% and 43%
Project 2 | 50 | 20 | 25 | 18 | 4 | 2 | 3 | 4 | 15 | 14 | 15 | - | Behind schedule Actual OWPA = 43%; Target OWPA = 70%; 10% of target OWPA = 7p.p; Behind schedule if actual OWPA is 63% and below
Project 3 | 25 | 15 | 30 | 20 | 6 | 7 | 8 | 5 | 14 | 10 | - | - | Ahead schedule Actual OWPA = 50%; Target OWPA = 40%; 10% of target OWPA = 4p.p; Ahead of schedule if actual OWPA is 44% and above
Project N
Programs
Program 1
Program 2
Program N
1 For locally-funded programs, target as of 31 December 2014 shall refer to the physical targets corresponding to the programmed utilization of available releases for CY 2014, i.e., from the use of new releases in CY 2014 and balances of past releases, continuing or carried forward to CY 2014, net of adjustments, but to exclude balances of releases continuing or carried forward to CY 2015.\
2 For locally-funded programs, target for CY 2015 shall refer to the physical targets corresponding to the programmed utilization of available releases for CY 2015, i.e., from the use of new releases in CY 2015 and balances of past releases continuing or carried forward to CY 2015.
3 For locally-funded programs, actual physical accomplishment as of 31 December 2014 shall refer to the actual physical accomplishment corresponding to the programmed utilization of available releases for CY 2014, i.e., from the use of new releases in CY 2014 and balances of past releases, continuing or carried forward to CY 2014, net of adjustments, but to exclude balances of releases continuing or carried forward to CY 2015.
4 For locally-funded programs, actual physical accomplishment for CY 2015 shall refer to the actual physical accomplishment corresponding to the programmed utilization of available releases for CY 2015, i.e., from the use of new releases in CY 2015 and balances of past releases continuing or carried forward to CY 2015.
5 Sum of columns D to M should equal 100% (i.e., actual accomplishment as of end 2015 and future targets until the end of project implementation). For locally-funded programs, only supply the CY 2016 targets.
6 Indicate the physical status as of end of CY 2015, whether: completed, ahead of schedule, on schedule, or behind schedule (see guidelines on how to determine physical status based on the OWPA.)
7 Indicate whether the project would be completed on schedule. In case no physical accomplishment or output, please indicate preparatory activities undertaken. If there is negative slippage as of end of CY 2015, cite reason(s) with the details provided in Table 4A.
Prepared by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: ________________
(Signature over printed name)

## Table 3B
For GFIs
CY 2014 ODA PORTFOLIO REVIEW
Table 3B
Components and Physical Outputs of Projects and Programs
GFI Name
As of December 31, 2015
PROJECT/ PROGAM TITLE AND COMPONENTS | OUTPUTS | TARGET |  | ACTUAL |  | Validated | Remarks1
|  | As of 31 | CY 2015 | As of 31 | CY 2015 | Agency MFO(s)
|  | Dec. 2014 |  | Dec. 2014 |  | Supported
Projects
Project 1
Component 1 | Output 1 |  |  |  |  | MFO Statement 1
Output 2
Output 3
Component 2 | Output 1 |  |  |  |  | MFO Statement 2
Output 2
Output 3
Project 2
Component 1 | Output 1
Output 2
Output 3
Component 2 | Output 1
Output 2
Output 3
Programs
Program 1
Component 1 | Output 1
Output 2
Output 3
Component 2 | Output 1
Output 2
Output 3
1 For locally-funded programs, target as of 31 December 2014 shall refer to the physical targets corresponding to the programmed utilization of available releases for CY 2014, i.e., from the use of new releases in CY 2014 and balances of past releases, continuing or carried forward to CY 2014, net of adjustments, but to exclude balances of releases continuing or carried forward to CY 2015.\
2 For locally-funded programs, target for CY 2015 shall refer to the physical targets corresponding to the programmed utilization of available releases for CY 2015, i.e., from the use of new releases in CY 2015 and balances of past releases continuing or carried forward to CY 2015.
3 For locally-funded programs, actual physical accomplishment as of 31 December 2014 shall refer to the actual physical accomplishment or outputs corresponding to the programmed utilization of available releases for CY 2014, i.e., from the use of new releases in CY 2014 and balances of past releases, continuing or carried forward to CY 2014, net of adjustments, but to exclude balances of releases continuing or carried forward to CY 2015.
4 For locally-funded programs, actual physical accomplishment for CY 2015 shall refer to the actual physical accomplishment or outputs corresponding to the programmed utilization of available releases for CY 2015, i.e., from the use of new releases in CY 2015 and balances of past releases continuing or carried forward to CY 2015.
5 Indicate whether the outputs would be delivered as scheduled, and if not, the factors that affected the delayed or non-delivery of said outputs.
Prepared by: ______________________________ |  |  | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: _____________________________
(Signature over printed name)

## Table 3C
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 3C
Project/Program Component(s) Addressing Climate Change and Contributing to Disaster Risk Reduction
GFI Name
As of December 31, 2015
(Kindly indicate the component/s of projects and programs that address climate change mitigation/adaptation or disaster risk reduction by indicating the cost/amount
allocated for each initiative).
Project Title | CC1/DRR Initiative Amount (PM) |  |  | Total | Remarks2
| Adaptation | Mitigation | DRR
Projects
Project 1 (Sample) |  |  |  |  | Engineering designs include measures for erosion control and reduction of soil degradation.
Component 1: | 0.1 | 0.3 |  | 0.4
Component 2: |  |  | 5.5 | 5.5
Component N |  |  | 2 | 2
Programs |  |  |  | 0
Program 1 |  |  |  | 0
Component 1: |  |  |  | 0
Component 2: |  |  |  | 0
0
0
Component N |  |  |  | 0
1Climate Change Initiatives (National Framework Strategy on Climate Change 2010-2022):
Mitigation - aims to facilitate the transition towards low greenhouse gas emissions for sustainable development
a) energy efficiency and conservation; b) realization of the full potential of the country’s renewable energy; c) improvement of the transport sector through the uptake of
alternative fuels and expansion of mass transport systems; d) making use of energy--efficient design and materials for public infrastructure and settlements; e)
reduction of emissions from deforestation and forest degradation; and g) waste management.
Adaptation - points towards building the adaptive capacity of communities and increasing the resilience of natural ecosystems to climate change
a) enhancement of vulnerability and adaptation assessments; b) integrated ecosystem-based management; c) water governance and management; d) promotion of a
climate-responsive agriculture; e) support climate-responsive health sector; and f) encourage climate-proofing infrastructure
2Description of CC/DRR initiatives under the relevant component(s) of the project/program.
Prepared by: ______________________________ |  |  | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: _____________________________
(Signature over printed name)

## Table 3D
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 3D
Projects/Programs with Damaged Output(s), Incomplete Output(s) or Sustainability Issue(s)
GFI Name
As of December 31, 2015
Projects/programs with outputs damaged in CY 2015
Project/Program Title | Year Completed | Description of Damaged Output(s)* | Actions taken/ being taken to address the damaged output(s) | Actions to be taken to address the damaged output(s)
Projects
Programs
* with attribution to specific events (e.g. Typhoon Lando)
Closed projects/programs in CY 2015 with incomplete outputs
Project/Program Title | Year Completed | Description of the Incomplete Output(s) * | Actions taken/ being taken to address the incomplete output(s) | Actions to be taken to address the incomplete output (s)
Projects
Programs
Completed projects/programs in 2015 with sustainability issues
Project/Program Title | Year Completed | Sustainability Issue(s) * | Actions taken/ being taken to address the issue(s) | Actions to be taken to address the issue(s)
Projects
Programs

## Table 4A
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 4A
Problem Analysis of Projects and Programs
GFI Name
As of December 31, 2015
PROJECT/ | PROBLEM/ ISSUE IDENTIFIED1 | ISSUE DETAILS | ISSUE STATUS (CURRENT OR RESOLVED) | ACTIONS TAKEN/BEING TAKEN2 | ACTIONS TO BE TAKEN IN CY 2016 AND BEYOND3 | REMARKS4
PROGRAM
Projects
Project 1
Project 2
Project N
Programs
Program 1
Program 2
Program N
1Use typology of issues indicated in the Guidelines
2For both current or outstanding issues/problems and those which ended in 2015, include actions taken/being taken by the agency on recommendations during the CY 2014 ODA Portfolio Review
3Plan of action to address currrent or outstanding isuues/problems.
4For problems identified as current or outstanding, provide updates (as of 2016) on the actions taken, if any, and discuss the probability of achieving project objectives (i.e., low, moderate, or high)
Prepared by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
Approved by: _________________________________ |  |  | Date: ________________
(Signature over printed name)

## Table 4B
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 4B
Assumptions/Risk Register
GFI Name
As of December 31, 2015
PROJECT/ PROGRAM TITLE | ASSUMPTIONS/RISK CATEGORY1 | ASSUMPTIONS/RISK DESCRIPTION (POTENTIAL IMPACTS ON PROJECT COMPLETION) | MANAGEMENT STRATEGIES/ CONTINGENCY MEASURES | RISK STATUS2 AND UPDATES/REMARKS (RISK STATUS CATEGORIES: CURRENT, ENDED, MITIGATED, OCCURRED)
(1) | (2) | (3) | (4) | (5)
Projects | example: | example: | example: | example:
Project 1 | Operation and Maintenance | 1. Farmer Irrigation Organizations (FIO) operationalized and are tasked to among others undertake the maintenance of project facilities. | 1. a. Additional personnel for organizing FIOs are being hired. 1. b. Continous capacity building activities are being undertaken by implementing agency | Current. 1.a. As of ___ implementing agency has hired ___ of target additional personnel to undertake FIO organizing 1.b.Implementing agency has undertaken (no.) of capacity building activities for the FIOs 1.c. Management transfer agreements have been drafted
| LGU participation | 2. LGUs adhere to the MOAs | 2. Periodic consultations to secure buy in of LGUs | 2. Implementing agency conducted (no.) of consultations.
| Contractor performance | 3. Contractor underperformance. The contractor is unable to deliver on time and outputs are below standards increasing cost and incurring time overruns. | 3. An early contractor exit tol reduce the risk and cost of further underperformance | Current. 3. Implementing agency monthly monitors contractors performance to alert and mitigate slippages.
Programs | example: | example: | example: | example:
Program 1 | Start-up delays | Non-familiarity with budget policies by project management staff/personnel will extend preparation of budget delaying availability of funds | Start-up activities include briefing/coaching of all financial management personnel. | Current. Ongoing familiarization
|  | Unfamilairity on procurement procedures including the preparation of bid docmuments | Training of personnel on procurement law and bidding procedures before the start of project | Current. Ongoing training on procurment
1Use risk categories indicated in the Guidelines.
2Risk/Assumption Status categories:
- current - poses as a threat/enhancement to the project
- ended – is no longer a threat or a valid assumption
- mitigated – risk was mitigated
- occurred - risks not mitigated and has progressed as an issue/problem); OR, an assumption that has materialized
Prepared by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
Approved by: _________________________________ |  |  | Date: ________________
(Signature over printed name)

## Table 6B (hidden)
For GFIs
CY 2014 ODA Portfolio Review
Table 6B
Assumptions/Risk Register for (Project Title)
GOCC Name
Outcome level | Assumptions/Risk Category | Assumptions/Risk Description (Potential Impacts on Project Competion) | Management Strategies/ Contingency Measures | Risk Status (current or ended) | Remarks
(1) | (2) | (3) | (4) | (5) | (6)
Goal
Purpose
Output | example: | example: | example: | Current | example:
| Operation and Maintenance of the IS | a) Farmer Irrigation Organizations (FIO) operationalized | a) Additional personnel for organizing are being hired. |  | FIOs expected to sustain O&M of completed facilities
|  | b) NIA acceptance of completed project from contractor | b) PMO regular supervision of the work of the contractor to avoid rejection of the work done.
|  | c) O&M training provided | c) Ensure availability of NIA personnel to conduct the training
Activities | example: | example: | example: |  | example:
| Start-up delays | Non-familiarity with budget policies by project management staff/personnel will extend preparation of budget delaying availability of funds | Start-up activities include briefing/coaching of all financial management personnel. | Current | Ongoing familiarization
|  | Unfamilairity on procurement procedures including the preparation of bid docmuments | Training of personnel on procurement law and bidding procedures before the start of project
Prepared by: ______________________________ | Date: ________________
(Signature over printed name)
Approved by: _________________________________ | Date: ________________
(Signature over printed name)

## Table 5
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 5
Projects/Programs for Possible Restructuring/ICC Re-evaluation in CY 2016 (if applicable)
GFI Name
As of December 31, 2015
PROJECT/ | FUNDING SOURCE | DETAILS OF POSSIBLE PROJECT RE-STRUCTURING/ | REASON(S)/ JUSTIFICATION(S)
PROGRAM | (IF ODA) | ICC RE-EVALUATION IN CY 2016
TITLE
Projects
Project 1
Project 2
Project N
Programs
Program 1
Program 2
Program N
Prepared by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
Approved by: _________________________________ |  |  | Date: ________________
(Signature over printed name)

## Table 6
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 6
Project/Program Results
GFI Name
As of December 31, 2015
Project/Program Title : _______________________________________________________________________
OBJECTIVES | RESULTS INDICATOR/TARGET | ACTUAL | PDP RM INDICATOR(S)1
(Based on Logframe) | (Based on Logframe) | (Using Proxy or Logframe Indicators) | the project contributes to
Goal:
Objective statement (goal) | Indicator Target 1 (goal) | Actual Value for Indicator Target 1 (goal) as of (date)
| Indicator Target 2 (goal) | Actual Value for Indicator Target 2 (goal) as of (date)
| Indicator Target N (goal) | Actual Value for Indicator Target N (goal) as of (date)
Purpose:
Objective statement (purpose) | Indicator Target 1 (purpose) | Actual Value for Indicator Target 1 (purpose) as of (date)
| Indicator Target 2 (purpose) | Actual Value for Indicator Target 2 (purpose) as of (date)
| Indicator Target N (purpose) | Actual Value for Indicator Target N (purpose) as of (date)
1 May be downloaded using this link: http://www.neda.gov.ph/2015/05/07/philippine-development-plan-2011-2016-revalidated-results-matrices/
Prepared by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
Approved by: _________________________________ |  |  | Date: ________________
(Signature over printed name)

## Table 9B (hidden)
CY 2014 PORTFOLIO REVIEW
Table 9B
Funds Flow Timelines
GFI Name
As of December 31, 2014
Project Title/Funding Source | WA Amount Requested (US$M) | Withdrawal Application (WA) |  |  | BTr Notice |  | NCA Processing |  |  | Total Processing Time from WA to NCA Release (No. Of Days)
|  | WA Applied (Date Received by FS) | WA Release (Date Received by BTr) | WA Application to Release (No. Of Days) | BTr Notice (Date Received by IA) | WA Release to BTr Notice (No. Of Days) | Application for NCA (Date Received by DBM) | NCA Release Date (Received by IA) | BTr Notice to NCA Release (No. Of Days)
|  | (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9= 3+5+8)
Agency Total
Project 1
Withdrawal Application No. ___
Withdrawal Application No. ___
Withdrawal Application No. ___
Project 2
Withdrawal Application No. ___
Withdrawal Application No. ___
Withdrawal Application No. ___
Project 3
Withdrawal Application No. ___
Withdrawal Application No. ___
Withdrawal Application No. ___
Project N
Withdrawal Application No. ___
Withdrawal Application No. ___
Withdrawal Application No. ___
Prepared by: ______________________________ |  | (1): Date: _______________
(Signature over printed name)
Approved by: ______________________________ |  | (1): Date: _______________
(Signature over printed name)

## Table 9A (hidden)
Project Title: _________________________________________
GFI Name : _________________________________________
CY 2014 ODA PORTFOLIO REVIEW
Table 9A
PROCUREMENT MILESTONES (with contracts awarded or NTP issued in CY 2014)
|  | CONTRACT DESCRIPTION | START OF TENDERING PROCESS/ ADVERTISE-MENT | SUBMISSION AND OPENING OF BIDS | COMPLETION OF BID EVALUATION |  | CONTRACT AWARD | ISSUANCE OF NOTICE TO PROCEED | TOTAL | CONCURRENCE OF FUNDING INSTITUTION** | NET OF FUNDING INSTITUTION'S PROCESSING TIME
[5 empty] | Technical | Financial |  |  | (no. of months)
|  |  | (mm/dd/yy) | (mm/dd/yy) | (mm/dd/yy) | (mm/dd/yy) | (mm/dd/yy) | (mm/dd/yy) |  | (no. of months) | (no. of months)
|  |  | (1) | (2) | (3) | (4) | (5) | (6) | (7=1+2+3+4+5+6) | (8) | (9=7 - 8)
Consulting Services
* | Contract Name/ Procurement Guidelines Used:
Amount (--M)
Accomplishment Date:
Target
Actual
Remarks
Civil Works
* | Contract Name/ Procurement Guidelines Used:
Amount (--M)
Accomplishment Date:
Target
Actual
Remarks
Goods (Equipment/Materials)
* | Contract Name/ Procurement Guidelines Used:
Amount (--M)
Accomplishment Date:
Target
Actual
Remarks
* Major Contracts awarded or NTP issued in 2008 (pls. use extra pages to reflect all major contracts)
** Indicate concurrence of Funding Institutions from the start of the tendering process up to contract award
Prepared by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: ________________
(Signature over printed name)

## Table 7
For GFIs
CY 2015 AGENCY PORTFOLIO REVIEW
Table 7
Lessons Learned Register for Projects/Programs
GFI Name
As of December 31, 2015
PROJECT/ PROGRAM TITLE | PROJECT/PROGRAM MANAGEMENT AREA/CATEGORY | PROGRAM/ PROJECT PHASE | SITUATION | LESSONS LEARNED*
Projects
Project 1 | Procurement | Implementation | Some items will not be delivered by the Contractor because these are not clearly specified in the signed contract. | In preparing the contract, make sure that the deliverables of the contractor are specific and specified clearly in details to avoid misunderstanding. Be sure that information are accurate and no gray areas before signing the contract.
Project 2
Project N
Programs
Program 1
Program 2
Program N
*Lessons learned for CY 2015 only.
Prepared by: ______________________________ |  |  | Date: _______________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: _______________
(Signature over printed name)