## Sheet1 (hidden)
QUALITY POLICY
| Quality product and services | Customer satisfaction | Continual improvement | Quality target | Development of people | Legal Requirements
Corporate Objectives | Deliver quality products and services that meet customer's needs and expectations. | Get rating of 3.0 | Conduct audit and meetings | 10% Increase | 1 Engineer to undergo training per year | Meeting the requirements of National Building Codes and International Standards.
Functional Objectives
Business Development | 100% complete and on time submission of pre-qualification documents. Completeness of information from clients to evaluate and comply to reuqirements. | ditto | Timely preparation and implementation of corrective and preventive actions on the identified non-conformances, customer complaints and/or other quality problems which are taken up during meetings and verified through audits. | To meet the sales targets for 2015 | To train at least 1 eningeer either overseas or local to keep abreast with the latest technology.
Quantity Surveying | Completeness of the required documents and timeliness of submission | ditto |  | 100% accuracy of estimate
Design & Engineering | Acceptance of design methodology | ditto |  | 100% acceptance of application development and implementation using design tools.
| Conformance with plans and specifications of the contract/consultant | ditto |  | 100% compliance based on actual condition, intent design and specifications
Production | 100% in accordance with the approved shop drawings/fabrication drawings | ditto |  | 100% conformance with the specifications and completed as per production schedule
Material Management | 100% conformance to the specified requirements | ditto |  | 100% compliance to specifications
| Timeliness of delivery of materials | ditto |  | 100% compliance to the delivery schedule of the requisitioner
Project Management | 100% compliance to project plan | ditto |  | 100% compliance to delivery requirements of the project.
| Timeliness of delivery of resources | ditto |  | 100% compliance to mobilization schedule
| Durability of the approved material/product | ditto |  | 100% compliance with the systems design specification
| 100% conformance to construction plan and shop drawings | ditto |  | 100% conformance to project completion of specified schedule of the client
| Durability of the installed system | ditto |  | 100% conformance to material specification
| 100% completeness of the installed system | ditto |  | 100% completion as per schedule by client
| Acceptability of installed system and timeliness of handover | Rating of client survey not less than 3.0 "satisfactory"
Accounting | Collection of sales invoices issued based on credit terms | ditto |  | 70% collection based on credit terms and reduce past dues by 15% every quarter
Office Administration | Timely response to required vehicles, maintenance of machineries and equipment needs in daily operations. | ditto |  | Provide 100% assistance in daily business operations and company events/activities.
Human Resources | Timeliness in hiring qualified employees | ditto |  | Provide 100% manpower requirement
From the corporate objectives the functional objectives are established.
The quality policy provides as the framework for establishing quality objectives

## CONTEXT
Address: 12 St. Josemaria Escriva Drive, Ortigas Center, Pasig City 1605 Philippines Tel: (+632) 631 0945 to 56 ¦ E-mail: info@neda.gov.ph ¦ Website: www.neda.gov.ph
ORGANIZATIONAL CONTEXT
PURPOSE | (may be based on the Mandate / Mission or Quality Policy of the organization) |  |  | Rev. No.:
STRATEGIC DIRECTION: | (Consider the Vision, or any established strategic direction of the organization) |  |  | Date:
EXTERNAL ENVIRONMENT
Perspective | Positive Issues / Factors (Opportunities) | Negative Issues / Factors (Threats) | Extent | Potential Impact to Intended Results
POLITICAL | Pro-business political agenda of new Administration (N) |  | International; National
ECONOMIC / FINANCIAL |  | fluctuating peso and rising inflation | National; Regional; Local
SOCIAL
TECHNOLOGICAL
LEGAL
ENVIRONMENTAL
CULTURAL
COMPETITION / MARKET
Short narrative description of the organization's external environment: (summarize the issues listed the above matrix and provide proper perspective to enable a clearer picture of the said issues))
NEDA ICC operates under a new administration whose policies include being business-friendly (e.g. plans to bring down corporate taxes), strong governance on anti-drug and anti-corruption; and fluctuating foreign exchange. ….
INTERNAL ENVIRONMENT
ASPECT / Perspective | Positive Issues / Factors (Strengths) | Negative Issues / Factors (Weaknesses) |  | Potential Impact to Intended Results
VALUES | Punctuality, Dependability, Commitment, Loyalty, Professionalism, Leadership
CULTURE | Risk-taker; can take complext projects with high risk levels but with potentially big returns
KNOWLEDGE | People are technically equipped | Lacks alternate competent personnel
PERFORMANCE | Outcomes (OO), MFOs, Objectives (OPCR) are consistently achieved
Short narrative description of the organization's internal environment: (summarize the issues listed the above matrix and provide proper perspective to enable a clearer picture of the said issues))
NEDA CO - ICC operates in an internal environment where personal values on commitment, loyalty, professionalism, dependability are strongly embedded in the psyche of the individuals. …

## FUNCTIONAL OBJECTIVE
Address: 12 St. Josemaria Escriva Drive, Ortigas Center, Pasig City 1605 Philippines Tel: (+632) 631 0945 to 56 ¦ E-mail: info@neda.gov.ph ¦ Website: www.neda.gov.ph
RISK REGISTER
FUNCTIONAL QUALITY OBJECTIVE RISK ASSESSMENT
Department: Public Investment Staff / ICC Core Secretariat | [5 empty] | Date Prepared: 29 December 2016 |  |  |  | Rev. No.: 0 |  |  |  | Code:
QUALITY OBJECTIVE | CONTEXT (functional / process) |  | RISK DEFINITION - Potential Problem, Failure or Uncertainty | POTENTIAL EFFECT(S) / CONSEQUENCES | TYPE* | EXISTING CONTROL MEASURE(S), if any | RISK ASSESSMENT |  |  |  |  | RISK RE-ASSESSMENT
| Positive Issues | Negative Issues |  |  |  |  | IMPACT | LIKELIHOOD | RATING | EVALUATION | Risk Control / Opportunity Management Plan (RCP / OMP) | IMPACT | LIKELIHOOD | RATING | EVALUATION | Risk Control / Opportunity Management Plan (RCP / OMP)
POLICY FORMULATION: 90% of policies timely and accurately drafted | Institutional memory of ICC members and the NEDA Secretariat Political will | Incomplete / inaccurate and/or untimely submission of inputs from relevant units | Incomplete and/or inaccurate inputs from relevant units | Ineffective or inaccurate formulated policy | R | Identify required policy inputs from relevant units and agencies , including any existing or previous policies as reference | 3 | 2 | 6 | NOT SIGNIFICANT | n/a
|  |  | Untimely submission of inputs from the relevant units | Delayed issuance of policy resulting to (i) prolonged; (ii) confusion in the appraisal process | R | Regular coordination with the relevant units (verified through written communication) | 3 | 3 | 9 | NOT SIGNIFICANT | n/a
* Type of Effect - R (Risk or negative effect); O - Opportunity (positive effect)
Prepared by: |  |  |  | Approved by:

## PROCESS
Address: 12 St. Josemaria Escriva Drive, Ortigas Center, Pasig City 1605 Philippines Tel: (+632) 631 0945 to 56 ¦ E-mail: info@neda.gov.ph ¦ Website: www.neda.gov.ph
RISK REGISTER
PROCESS RISK ASSESSMENT
Department: ICC Core Secretariat / Public Investment Staff |  |  |  | Date Prepared: 29 December 2016 |  |  |  | Rev. No.: 0 |  |  |  | Code:
PROCESS | Policy Formulation
PROCESS STEP | RISK DESCRIPTION - Potential Problem / Failure / Uncertainty | POTENTIAL EFFECT(S) / CONSEQUENCES | Type* | EXISTING CONTROL MEASURE(S), if any | RISK ASSESSMENT |  |  |  |  | RISK RE-ASSESSMENT
[5 empty] | IMPACT | LIKELIHOOD | RATING | EVALUATION | Risk Control / Opportunity Management Plan (RCP / OMP) | IMPACT | LIKELIHOOD | RATING | EVALUATION | Risk Control / Opportunity Management Plan (RCP / OMP)
Identification of policy need and required inputs for policy development | Incomplete and/or inaccurate identified required inputs for policy development | i. Need to re-draft policy ii. Issued policy not responsive to address the issue at hand | R | Maintained database of existing policies | 3 | 2 | 6 | NOT SIGNIFICANT | n/a
Conduct of study in coordination with relevant units | Incomplete and/or inaccurate inputs from relevant units | Delayed issuance of policy resulting to (i) prolonged; (ii) confusion in the appraisal process | R | Conduct of additional research to cover incomplete information | 3 | 2 | 6 | NOT SIGNIFICANT | n/a
| Unavailability of data |  | R | Database with pertinent information on ICC related data (NB approved projects, ODA pipeline, IPAM) | 3 | 2 | 6 | NOT SIGNIFICANT | n/a
Drafting and review of policy issuance and/or cover memorandum to the ICC | Untimely submission of inputs from the relevant units | Delayed issuance of policy resulting to (i) prolonged; (ii) confusion in the appraisal process | R | Regular coordination with the relevant units | 3 | 3 | 9 | NOT SIGNIFICANT | n/a
| On time receipt of accurate inputs from the relevant units | Timely issuance of policy resulting to better appraisal process | O |  | 3 | 3 | 9 | NOT SIGNIFICANT | n/a
Presentation of the Policy Recommendations to the ICC for its Review and Approval | Receipt of relevant inputs/recommendations from ICC members | Improved policy resulting to more effective and efficient appraisal process | O |  | 3 | 3 | 9 | NOT SIGNIFICANT | n/a
Dissemination of the policy issuance to all concerned | Untimely signing of the policy issuance by the signatories | Delayed issuance of policy resulting to (i) prolonged; (ii) confusion in the appraisal process | R | Regular coordination with relevant units | 3 | 3 | 9 | NOT SIGNIFICANT | n/a
* Type of Effect - R (Risk or negative effect); O - Opportunity (positive effect)
Prepared by: |  |  |  | Approved by:

## RMP (hidden)
RISK MANAGEMENT PLAN
Department: Purchasing |  |  | s |  |  |  | Rev. No.: ___________
Item No. | RISK DESCRIPTION | POTENTIAL EFFECT(S) | RISK CONTROL PLAN (Strategies, Activities) | Responsible | Timelines |  | Resource Needs | MONITORING
[8 empty] | FREQUENCY | WHO | RECORD
[5 empty] | Start | End
PUR-RMP-01 | Delayed receipt of quotation from suppliers | Delayed project completion affecting billing / revenue; Results to weak project cash flow | 1) Regular monitoring of quotations for PRFs. 2)
2)
Possible Management Actions – to address risks
1) Avoidance |  | Avoiding risk,
2) Acceptance |  | Taking risk to pursue an opportunity,
3) Elimination |  | Eliminating the risk source,
4) Reduction |  | Changing the likelihood (L) or consequence (C),
5) Allocation |  | Sharing the risk,
6) Retention |  | Retaining risk by informed decision
Possible Management Options – to address opportunities
1) adoption of new practices,
2) launching new products,
3) opening new markets,
4) addressing new customers,
5) building partnerships,
6) using new technology,
7) other desirable and viable possibilities to address the organization or its customers’ needs.