## Sheet1
QUALITY POLICY
| Quality product and services | Customer satisfaction | Continual improvement | Quality target | Development of people | Legal Requirements
Corporate Objectives | Deliver quality products and services that meet customer's needs and expectations. | Get rating of 3.0 | Conduct audit and meetings | 10% Increase | 1 Engineer to undergo training per year | Meeting the requirements of National Building Codes and International Standards.
Functional Objectives
Business Development | 100% complete and on time submission of pre-qualification documents. Completeness of information from clients to evaluate and comply to reuqirements. | ditto | Timely preparation and implementation of corrective and preventive actions on the identified non-conformances, customer complaints and/or other quality problems which are taken up during meetings and verified through audits. | To meet the sales targets for 2015 | To train at least 1 eningeer either overseas or local to keep abreast with the latest technology.
Quantity Surveying | Completeness of the required documents and timeliness of submission | ditto |  | 100% accuracy of estimate
Design & Engineering | Acceptance of design methodology | ditto |  | 100% acceptance of application development and implementation using design tools.
| Conformance with plans and specifications of the contract/consultant | ditto |  | 100% compliance based on actual condition, intent design and specifications
Production | 100% in accordance with the approved shop drawings/fabrication drawings | ditto |  | 100% conformance with the specifications and completed as per production schedule
Material Management | 100% conformance to the specified requirements | ditto |  | 100% compliance to specifications
| Timeliness of delivery of materials | ditto |  | 100% compliance to the delivery schedule of the requisitioner
Project Management | 100% compliance to project plan | ditto |  | 100% compliance to delivery requirements of the project.
| Timeliness of delivery of resources | ditto |  | 100% compliance to mobilization schedule
| Durability of the approved material/product | ditto |  | 100% compliance with the systems design specification
| 100% conformance to construction plan and shop drawings | ditto |  | 100% conformance to project completion of specified schedule of the client
| Durability of the installed system | ditto |  | 100% conformance to material specification
| 100% completeness of the installed system | ditto |  | 100% completion as per schedule by client
| Acceptability of installed system and timeliness of handover | Rating of client survey not less than 3.0 "satisfactory"
Accounting | Collection of sales invoices issued based on credit terms | ditto |  | 70% collection based on credit terms and reduce past dues by 15% every quarter
Office Administration | Timely response to required vehicles, maintenance of machineries and equipment needs in daily operations. | ditto |  | Provide 100% assistance in daily business operations and company events/activities.
Human Resources | Timeliness in hiring qualified employees | ditto |  | Provide 100% manpower requirement
From the corporate objectives the functional objectives are established.
The quality policy provides as the framework for establishing quality objectives

## CONTEXT (hidden)
Address: 12 St. Josemaria Escriva Drive, Ortigas Center, Pasig City 1605 Philippines Tel: (+632) 631 0945 to 56 ¦ E-mail: info@neda.gov.ph ¦ Website: www.neda.gov.ph
ORGANIZATIONAL CONTEXT
PURPOSE | (may be based on the Mandate / Mission or Quality Policy of the organization) |  |  | Rev. No.:
STRATEGIC DIRECTION: | (Consider the Vision, or any established strategic direction of the organization) |  |  | Date:
EXTERNAL ENVIRONMENT
Perspective | Positive Issues / Factors (Opportunities) | Negative Issues / Factors (Threats) | Extent | Potential Impact to Intended Results
POLITICAL | Pro-business political agenda of new Administration (N) |  | International; National
ECONOMIC / FINANCIAL |  | fluctuating peso and rising inflation | National; Regional; Local
SOCIAL
TECHNOLOGICAL
LEGAL
ENVIRONMENTAL
CULTURAL
COMPETITION / MARKET
Short narrative description of the organization's external environment: (summarize the issues listed the above matrix and provide proper perspective to enable a clearer picture of the said issues))
NEDA ICC operates under a new administration whose policies include being business-friendly (e.g. plans to bring down corporate taxes), strong governance on anti-drug and anti-corruption; and fluctuating foreign exchange. ….
INTERNAL ENVIRONMENT
ASPECT / Perspective | Positive Issues / Factors (Strengths) | Negative Issues / Factors (Weaknesses) |  | Potential Impact to Intended Results
VALUES | Punctuality, Dependability, Commitment, Loyalty, Professionalism, Leadership
CULTURE | Risk-taker; can take complext projects with high risk levels but with potentially big returns
KNOWLEDGE | People are technically equipped | Lacks alternate competent personnel
PERFORMANCE | Outcomes (OO), MFOs, Objectives (OPCR) are consistently achieved
Short narrative description of the organization's internal environment: (summarize the issues listed the above matrix and provide proper perspective to enable a clearer picture of the said issues))
NEDA CO - ICC operates in an internal environment where personal values on commitment, loyalty, professionalism, dependability are strongly embedded in the psyche of the individuals. …

## ORGANIZATIONAL (hidden)
Address: 12 St. Josemaria Escriva Drive, Ortigas Center, Pasig City 1605 Philippines Tel: (+632) 631 0945 to 56 ¦ E-mail: info@neda.gov.ph ¦ Website: www.neda.gov.ph
ORGANIZATIONAL QUALITY OBJECTIVE RISK ASSESSMENT MATRIX - 2016
[6 empty] | Date prepared: _________________________ |  |  |  | Rev. No.: ___________
Organizational Outcomes (OO) / Major Final Outputs (MFO) | CONTEXT (organizational) |  | RISK DEFINITION - Potential Problem, Failure or Uncertainty | POTENTIAL EFFECT(S) / CONSEQUENCES |  | CONTROL MEASURES, if any | RISK ASSESSMENT |  |  |  | Control / Management Plan (RCP / OMP) | RISK RE-ASSESSMENT |  |  |  | RCP / OMP
| Positive Issues | Negative Issues |  |  | TYPE |  | IMPACT | LIKELIHOOD | RISK RATING | Significant? |  | IMPACT | LIKELIHOOD | RISK RATING | Significant?

## FUNCTIONAL (hidden)
Address: 12 St. Josemaria Escriva Drive, Ortigas Center, Pasig City 1605 Philippines Tel: (+632) 631 0945 to 56 ¦ E-mail: info@neda.gov.ph ¦ Website: www.neda.gov.ph
FUNCTIONAL QUALITY OBJECTIVE RISK ASSESSMENT MATRIX
Department: Purchasing | [5 empty] | Date prepared: _________________________ |  |  |  | Rev. No.: ___________
QUALITY OBJECTIVE | CONTEXT (functional / process) |  | RISK DEFINITION - Potential Problem, Failure or Uncertainty |  | POTENTIAL EFFECT(S) / CONSEQUENCES | CONTROL MEASURES | RISK ASSESSMENT |  |  |  | Control / Management Plan (RCP / OMP) | RISK ASSESSMENT |  |  |  | RCP / OMP
| Positive Issues | Negative Issues |  |  |  |  | IMPACT | LIKELIHOOD | RATING | Significant? |  | IMPACT | LIKELIHOOD | RATING | Significant?
100% compliance to specification and delivery requirements of the project | Adequate stocks maintained; short PR/PO process cycle time | No reordering quantities (stock levelsare very minimal) | Incomplete or inaccurate specifications in PRs | R | Project delay resulting to penalties | Established 3 to 5 WD for quote submission | 3 | 3 | 9 | NOT SIGNIFICANT | n/a | 3 | 3 | 9 | NOT SIGNIFICANT | n/a
|  |  |  | R | Rejection by client and subsequent replacement may delay the project | Review PR/PO by approving authority | 5 | 2 | 10 | SIGNIFICANT | PUR-RCP-1 | 5 | 2 | 10 | SIGNIFICANT | PUR-RCP-1
|  |  | On-time material delivery results to timely nstallation of parts / materials | O | On-time billing | PM-INST-01 (Procedure) | 3 | 2 | 6 | NOT SIGNIFICANT | n/a | 3 | 2 | 6 | NOT SIGNIFICANT | n/a

## FUNCTIONAL OBJECTIVE
Address: 12 St. Josemaria Escriva Drive, Ortigas Center, Pasig City 1605 Philippines Tel: (+632) 631 0945 to 56 ¦ E-mail: info@neda.gov.ph ¦ Website: www.neda.gov.ph
RISK REGISTER
FUNCTIONAL QUALITY OBJECTIVE RISK ASSESSMENT
Department: Public Investment Staff | [5 empty] | Date Prepared: 29 December 2016 |  |  |  | Rev. No.: 0 |  |  |  | Code:
QUALITY OBJECTIVE | CONTEXT (functional / process) |  | RISK DEFINITION - Potential Problem, Failure or Uncertainty | POTENTIAL EFFECT(S) / CONSEQUENCES | TYPE* | EXISTING CONTROL MEASURE(S), if any | RISK ASSESSMENT |  |  |  |  | RISK RE-ASSESSMENT
| Positive Issues | Negative Issues |  |  |  |  | IMPACT | LIKELIHOOD | RATING | EVALUATION | Risk Control / Opportunity Management Plan (RCP / OMP) | IMPACT | LIKELIHOOD | RATING | EVALUATION | Risk Control / Opportunity Management Plan (RCP / OMP)
POST-ICC MEETING
Timely and Accurate Preparation, Validation and Issuance of ICC Action Letter (target: 90% accuracy and timeliness; 5 working days) | 1. Meeting recordings and other materials are always available. 2. Multiple levels of review and approval ensures accuracy and correctness of the contents of the letter. | 1. Heavy workload of technical staff. 2. Multiple levels of review and approval cause delay especially in instances that signatories are unavailable. | > The heavy workload of technical staffs and the multiple levels of review and approval of the draft ICC Action letter causes the untimely delivery of the ICC instructions to the proponent agency. | The untimely delivery of the ICC instructions to the proponent might cause delay in their compliance to the same, which, might also delay the project implementation. | R | The prescribed timeline in the preparation of ICC Letters should be strictly followed. The technical staff in charge should inform division chief immediately in case the deadline could not be met due to another equally urgent task so that the workload will be distributed. | 3 | 3 | 9 | NOT SIGNIFICANT | n/a
Timely and Accurate Preparation, Validation and Issuance of ICC Minutes of the Meeting (target: 90% accuracy and timeliness; 8 working days) | 1. Meeting recordings and other materials are always available. 2. Multiple levels of review and approval ensures accuracy and correctness of the contents of the minutes. | 1. Heavy workload of technical staff. 2. The differing writing style and technique of the technical staffs causes inconsistency in the consolidation of the final minutes. | > The heavy workload of technical staffs causes the untimely submission of the materials to the ICC Members. | The untimely submission of the ICC minutes to the ICC Core Secretariat might cause delay in the provision of the materials to the ICC Members in advance for their review. | R | The prescribed timeline in the preparation of ICC Minutes should be strictly followed. The technical staff in charge should inform division chief immediately in case the deadline could not be met due to another equally urgent task so that the workload will be distributed. | 3 | 3 | 9 | NOT SIGNIFICANT | n/a
|  |  | > Inconsistent style in the writing of the minutes per project. | Inconsistent style in the writing of the minutes per project will affect the quality of the final minutes. | R | Technical staffs should be given a crash course in minutes writing to build up speed and consistency in writing. | 3 | 3 | 9 | NOT SIGNIFICANT | n/a
Timely and accurate records filing and updating of database (target: 90% accuracy and timeliness; 2 working days for both filing and updating) |  | 1. There is no uniform filing system among the divisions. And there is limited storage area for records. 2. No readily accessible database of projects. | The lack of storage space, and a system of records keeping greatly affects the proper filing of projetc records and documents. | If project records and documents are not filed properly, the quick retrieval of needed information is not possible. | R | Introduce an improved system of records filing and allocate enough room for storage of records and documents ***None. RCP | 4 | 4 | 16 | SIGNIFICANT | RCP-PIS-01
|  |  | Techinal staffs, financing divisions have their own offline database which is not updated regularly and accessible. | If there is no functional and easy to use project database, the provision of timely information to our principals is a challenge. | R | Develop an easy to use project database that is easy to use and accessible. ***None. RCP | 4 | 4 | 16 | SIGNIFICANT | RCP-PIS-01
* Type of Effect - R (Risk or negative effect); O - Opportunity (positive effect)
Prepared by: |  |  |  | Approved by:

## PROCESS
Address: 12 St. Josemaria Escriva Drive, Ortigas Center, Pasig City 1605 Philippines Tel: (+632) 631 0945 to 56 ¦ E-mail: info@neda.gov.ph ¦ Website: www.neda.gov.ph
RISK REGISTER
PROCESS RISK ASSESSMENT
Department: NEDA Section: PIS |  |  |  | Date Prepared: 29 December 2016 |  |  |  | Rev. No.: 0 |  |  |  | Code:
PROCESS | QOP-ICC-CS-04 (POST-ICC)
PROCESS STEP | RISK DESCRIPTION - Potential Problem / Failure / Uncertainty | POTENTIAL EFFECT(S) / CONSEQUENCES | Type* | EXISTING CONTROL MEASURE(S), if any | RISK ASSESSMENT |  |  |  |  | RISK RE-ASSESSMENT
[5 empty] | IMPACT | LIKELIHOOD | RATING | EVALUATION | Risk Control / Opportunity Management Plan (RCP / OMP) | IMPACT | LIKELIHOOD | RATING | EVALUATION | Risk Control / Opportunity Management Plan (RCP / OMP)
Preparation, Validation, and Issuance of ICC Letter to the Proponent Agency (PA)/ Implementing Agency (IA)
Drafting of ICC Action Letter (2 working days) | Insufficient staff capacity to completely and accurately capture the ICC meeting deliberations as well as draft a grammatically correct ICC action letter | Incomplete, inaccurate, grammatically incorrect draft of the ICC action letter | R | Provide re-tooling/training on technical writing; Division Chiefs to edit/proofread the draft letter ***suggestion for DIS/ODDG to edit for consistency*** | 3 | 2 | 6 | NOT SIGNIFICANT | n/a
| Heavy workload assignment of the Technical Staff | Delay in submission of draft ICC action letter | R | Division Chiefs to re-assign some conflicting work assignments as needed; Use of Routing Slip and Monitoring Log Sheet | 3 | 2 | 6 | NOT SIGNIFICANT | n/a
Recording and release of the signed routing slip and cleared draft ICC Action Letter | Error and/or delay in release of signed routing slip and cleared draft ICC action letter | Delay in validation of the draft ICC action letter | R | PIS Releasing Officer to ensure that the signed routing slip and cleared draft ICC action letter are received on time | 2 | 2 | 4 | NOT SIGNIFICANT | n/a
Validation of the draft ICC Action Letter (2 working days) | Insufficient staff capacity to accurately validate and/or provide correct comments/inputs on the draft ICC action letter | Inaccurate and grammatically incorrect draft of the ICC action letter | R | Provide re-tooling/training on technical writing; Division Chiefs to edit/proofread the draft letter and/or comments/inputs | 3 | 2 | 6 | NOT SIGNIFICANT | n/a
| Heavy workload assignment of the Technical Staff | Delay in submission of draft ICC action letter | R | Division Chiefs to re-assign some conflicting work assignments as needed; Use of Routing Slip and Monitoring Log Sheet | 3 | 2 | 6 | NOT SIGNIFICANT | n/a
Recording and release of the signed routing slip and validated draft ICC Action Letter | Error and/or delay in release of signed routing slip and validated draft ICC action letter | Delay in signing of the validated draft ICC action letter | R | Evaluating Staff/s and/or NRO/s Releasing Officer to ensure that the signed routing slip and validated draft ICC action letter are received on time | 2 | 2 | 4 | NOT SIGNIFICANT | n/a
Signing of ICC Action Letter (1 working day) | Unavailability of the ICC Chair/s to sign the ICC action letter | Delay in signing of the ICC action letter | R | ICC Chair/s to prioritize signing of the ICC action letter | 2 | 3 | 6 | NOT SIGNIFICANT | n/a
Recording and release of the signed ICC Action Letter | Error and/or delay in release of signed ICC action letter | Delay in compliance of Proponent Agency/ Implementing Agency to the ICC instructions, if any | R | PIS Releasing Officer to ensure that the signed ICC action letter is received on time | 2 | 2 | 4 | NOT SIGNIFICANT | n/a
Preparation, Validation, and Confirmation of ICC Minutes
Drafting of ICC Minutes (4 working days) | Insufficient staff capacity to completely and accurately capture the ICC meeting deliberations as well as draft a grammatically correct ICC Minutes | Incomplete, inaccurate, grammatically incorrect draft of the ICC Minutes | R | Provide re-tooling/training on technical writing; Division Chiefs to edit/proofread the draft ICC Minutes | 2 | 3 | 6 | NOT SIGNIFICANT | n/a
| Heavy workload assignment of the Technical Staff | Delay in submission of draft ICC Minutes | R | Division Chiefs to re-assign some conflicting work assignments as needed; Use of Routing Slip and Monitoring Log Sheet | 2 | 3 | 6 | NOT SIGNIFICANT | n/a
Recording and release of the signed routing slip and cleared draft ICC Minutes | Error and/or delay in release of signed routing slip and cleared draft ICC Minutes | Delay in validation of the draft ICC Minutes | R | PIS Releasing Officer to ensure that the signed routing slip and cleared draft ICC Minutes are received on time | 3 | 2 | 6 | NOT SIGNIFICANT | n/a
Validation of the draft ICC Minutes (2 working days) | Insufficient staff capacity to accurately validate and/or provide correct comments/inputs on the draft ICC Minutes | Inaccurate and grammatically incorrect draft of the ICC Minutes | R | Provide re-tooling/training on technical writing; Division Chiefs to edit/proofread the ICC Minutes and/or comments/inputs | 2 | 3 | 6 | NOT SIGNIFICANT | n/a
| Heavy workload assignment of the Technical Staff | Delay in submission of draft ICC Minutes | R | Division Chiefs to re-assign some conflicting work assignments as needed; Use of Routing Slip and Monitoring Log Sheet | 2 | 3 | 6 | NOT SIGNIFICANT | n/a
Recording and release of the signed routing slip and cleared draft ICC Minutes | Error and/or delay in release of signed routing slip and validated draft ICC Minutes | Delay in signing of the validated draft ICC Minutes | R | Evaluating Staff/s and/or NRO/s Releasing Officer to ensure that the signed routing slip and validated draft ICC Minutes are received on time | 3 | 2 | 6 | NOT SIGNIFICANT | n/a
Timely and accurate consolidation/ finalization of ICC Minutes | Heavy workload assignment of the Technical Staff | Delay in consolidation/ finalization of ICC Minutes | R | Division Chiefs to re-assign some conflicting work assignments as needed | 3 | 3 | 9 | NOT SIGNIFICANT | n/a
Records Filing and Database Updating
Filing of ICC Letters and Minutes and Updating of the Program/Project Database | Incorrect filing of ICC letters and Minutes; incorrect updating of the program/project database | Delay in retrieval of files; misleading information in the program/project database | R | PIS Administrative Secretary to follow the correct filing procedure (based on RCP); PIS Technical Staff to ensure correct entry of information in the program/project database; Use of Monitoring Log Sheet (based on RCP) | 2 | 4 | 8 | NOT SIGNIFICANT | n/a
* Type of Effect - R (Risk or negative effect); O - Opportunity (positive effect)
Prepared by: |  |  |  | Approved by:

## RMP (hidden)
RISK MANAGEMENT PLAN
Department: Purchasing |  |  | s |  |  |  | Rev. No.: ___________
Item No. | RISK DESCRIPTION | POTENTIAL EFFECT(S) | RISK CONTROL PLAN (Strategies, Activities) | Responsible | Timelines |  | Resource Needs | MONITORING
[8 empty] | FREQUENCY | WHO | RECORD
[5 empty] | Start | End
PUR-RMP-01 | Delayed receipt of quotation from suppliers | Delayed project completion affecting billing / revenue; Results to weak project cash flow | 1) Regular monitoring of quotations for PRFs. 2)
2)
Possible Management Actions – to address risks
1) Avoidance |  | Avoiding risk,
2) Acceptance |  | Taking risk to pursue an opportunity,
3) Elimination |  | Eliminating the risk source,
4) Reduction |  | Changing the likelihood (L) or consequence (C),
5) Allocation |  | Sharing the risk,
6) Retention |  | Retaining risk by informed decision
Possible Management Options – to address opportunities
1) adoption of new practices,
2) launching new products,
3) opening new markets,
4) addressing new customers,
5) building partnerships,
6) using new technology,
7) other desirable and viable possibilities to address the organization or its customers’ needs.