## Table 9
CY 2016 AGENCY PORTFOLIO REVIEW
Table 9
Actions Taken on Recommendations Made during the CY 2015 ODA Review
Department of Agrarian Reform
As of December 31, 2016
Project/Program Title | CY 2015 ODA Review | Timelines | Responsibility Center | Actions Taken
Recommendation(s)
Projects
*Agrarian Reform Communities (ARCP II) /ADB and OFID *Italian Agrarian Reform Community Development Support Program (IARCDSP)/Italy *Mindanao Sustainable Agriculture and Agrarian Development (MinSAAD)/JICA | Procurement Bottlenecks. DAR should exert all effort to fast-track targeted procurement in projects to avoid delays in project implementation. Thus, DAR should give immediate attention to and provide prompt resolution of all procurement bottlenecks through strict adherence to procurement timelines and observance of harmonized GPH-DP guidelines. For transparency and objectivity in the evaluation of bids, an inter-agency body may be formed as the Technical Working Group (TWG) or Selection/Evaluation Committee. | ASAP | Department of Agrarian Reform
*Agrarian Reform Communities (ARCP II)//ADB and OFID | Budget and Funds flow. DAR to closely monitor and assess budget/finances and timely liquidation of incurred expenses to ensure that funds are readily available. | ASAP | Department of Agrarian Reform
Prepared by: ______________________________ |  |  |  | Date: ________________
(Signature over printed name)
Approved by: _________________________________ |  |  |  | Date: ________________
(Signature over printed name)