## Table 9
CY 2016 AGENCY PORTFOLIO REVIEW
Table 9
Actions Taken on Recommendations Made during the CY 2015 ODA Review
Department of Energy
As of December 31, 2016
Project/Program Title | CY 2015 ODA Review | Timelines | Responsibility Center | Actions Taken
Recommendation(s)
Market Transformation Energy Through Introduction of Energy Efficient Electric Vehicles Project (E-Trike Project) | DOE must ensure timely delivery of 3,000 E-Trikes to the beneficiaries, as soon as Notice to Proceed is issued. This shall determine continuation of project implementation, and shall be the basis of the decision to pursue partial or full cancellation of the loan (which will be remanded to the ICC and NEDA Board for approval). | 2016-05-01 | DOE
| Provide NEDA and DOF a final list of LGUs/associations/groups who have expressed firm commitment as beneficiaries of the initial 3,000 units of E-trikes. | 2016-05-01 | DOE
| Set disbursement targets in 2016, taking into account the effect of the delays in bidding out E-trike units on financial disbursements. | 2016-05-01 | DOE
Mini-hydropower development project for Ifugao | Ensure sustainability of the facilities by confirming plans for O&M of outputs, focusing on specific budget measures and distribution of roles and responsibilities | 2016 and beyond | DOE and Provincial Government of Ifugao
Prepared by: ______________________________ |  |  |  | Date: ________________
(Signature over printed name)
Approved by: _________________________________ |  |  |  | Date: ________________
(Signature over printed name)