## Table 9
CY 2016 AGENCY PORTFOLIO REVIEW
Table 9
Actions Taken on Recommendations Made during the CY 2015 ODA Review
NGA Name
As of December 31, 2016
Project/Program Title | CY 2015 ODA Review | Timelines | Responsibility Center | Actions Taken
Recommendation(s)
Agency Specific
DOTr (formerly DOTC) | Improve portfolio performance (accomplish set financial and physical targets and provide NEDA quarterly scheduled target disbursement figures of all ongoing projects) |  | DOTr
| Continued provision of the following reports: a. quarterly progress reports b. physical implementation and risk/assumption monitoring |  | DOTr
| DOTr's consolidated quarterly report with the inclusion of complete financial performance |  | DOTr
Project
Capacity Enhancement of Mass Transit Systems in Metro Manila | Fast track procurement process and provide updates to NEDA | 2016 | Light Rail Transit Authority
Laguindingan Airport Development Project | Resolve issues related to titling of acquired lots for LADP | 2016 | LADP PMO
| Continue coordination with the Office of the Solicitor General regarding the legal measures to be taken | 2016-2017 | LADP PMO / Office of the Solicitor General
Maritime Safety Capability Improvement Project for the Philippine Coast Guard | Provide updates on the delivery of the ships as well as other issues encountered | 2016 | PCG
New Bohol Airport Construction and Sustainable Environment Project | Continue coordination with the Office of the Solicitor General to advance the issuance of writ of possession for the remaining lots under expropriation | 2016 | NBACSEPP PMO / Office of the Solicitor General
New CNS-ATM Development Project | Upon justification of contractor’s price escalation claim, DOTC to endorse the claim for NEDA review | 2016-2017 | DOTC-CAAP/NEDA
Prepared by: ______________________________ |  |  |  | Date: ________________
(Signature over printed name)
Approved by: _________________________________ |  |  |  | Date: ________________
(Signature over printed name)