## Table 9
CY 2016 AGENCY PORTFOLIO REVIEW
Table 9
Actions Taken on Recommendations Made during the CY 2015 ODA Review
NGA Name
As of December 31, 2016
Project/Program Title | CY 2015 ODA Review | Timelines | Responsibility Center | Actions Taken
Recommendation(s)
Projects
KALAHI CIDSS - National Community Driven Development Program (KC-NCDDP) | Continuously conduct supplementary training for newly-hired staff to better enhance handling of project requirements at the community/barangay-level |  | KC-NPMO, RPMO, and MCC
KALAHI-CIDSS MCC | Continue close monitoring of ongoing sub-projects to increase probability of completion by end of MCC Compact Agreement in May 2016. |  | NPMO
Social Welfare and Development Reform Project (SWDRP) and SWDRP-Additional Financing | In crafting the Implementation Completion Report (ICR), DSWD may consider tagging the Programs’ accomplishments with the relevant outcome indicators in the PDP-RM, as well as to generate lessons that can be used as input to the next SWDRP Programs |  | 4Ps PMO
Programs
Sustainable Livelihood Program (SLP) | Complete the hiring of Project Development Officers (PDO) and enhance private linkages to improve implementation of SLP’s Employment Facilitation Track
Prepared by: ______________________________ |  |  |  | Date: ________________
(Signature over printed name)
Approved by: _________________________________ |  |  |  | Date: ________________
(Signature over printed name)