## Table 9
CY 2016 AGENCY PORTFOLIO REVIEW
Table 9
Actions Taken on Recommendations Made during the CY 2015 ODA Review
NGA Name
As of December 31, 2016
Project/Program Title | CY 2015 ODA Review | Timelines | Responsibility Center | Actions Taken
Recommendation(s)
Projects
MWMP | Inform NEDA and DOF on LBP’s decision on the financing gap of the two concessionaires (MWCI and MWSI); and on the completion date of the North Pasig 1 network which was reported by Manila Water that completion will go beyond the loan closing date. | May 2016 | LBP
| Closely monitor progress of implementation of ongoing contracts. |  | LBP
| Fast track implementation of projects with permits from LGUs (Muntinlupa STPs and Valenzuela sewers) which was secured only during first quarter of 2016. |  | LBP
SSLDIP | Ensure completion of three ongoing projects: Sanitary Landfill (2) and Water Supply (1) | April 2016 | LBP
| Submit all withdrawal applications to WB | On or before April 2016 | LBP
| Submit Project Completion Report | October 2016 | LBP
ACSP | Continue proactive marketing of the facility to potential client borrowers. | Continuing | LBP
| Submit request to increase initial deposit of the project to NEDA for endorsement to DOF. | Immediately | LBP
CBFMMP | Submit Project Completion Report | June 2016 | LBP
Program |  |  | LBP
Yolanda Reconstruction Program | Follow-up with KfW the no objection on the two submitted contracts. | April-May 2016 | LBP
Prepared by: ______________________________ |  |  |  | Date: ________________
(Signature over printed name)
Approved by: _________________________________ |  |  |  | Date: ________________
(Signature over printed name)