## Table 9
CY 2016 AGENCY PORTFOLIO REVIEW
Table 9
Actions Taken on Recommendations Made during the CY 2015 ODA Review
NGA Name
As of December 31, 2016
Project/Program Title | CY 2015 ODA Review | Timelines | Responsibility Center | Actions Taken
Recommendation(s)
Projects
Provincial Towns Water Supply and Sanitation Project (PTWSSP) Phase III | (1) For PMO to prioritize activities and resources and prepare a sound exit strategy and if possible a realistic work and financial plan to complete the remaining works and deliverables. | CY 2016 and Beyond | LWUA
| (2) Ensure budget requirement of the project is allocated until completion |  | LWUA
| (3) Submit regular status report on the progress of implementation on the uncompleted project outputs |  | LWUA
| (4) Revisit guidelines/timelines in conducting economic-financial evaluation of water supply proposals without sacrificing the required construction work schedule and trainings to be conducted |  | LWUA
| (5) Allocate time to conduct a Lessons Learned workshop and to prepare the PCR of the project |  | Project PMO
| (6) Conduct ex-post evaluation study of the project (KfW funds) to assess and properly document implementation issues, lessons learned, best practices if any. Lessons learned for the project can be used in improving LWUA’s planning process and selection of beneficiary WDs. |  | LWUA/Ex-post Evaluation Team
Prepared by: ______________________________ |  |  |  | Date: ________________
(Signature over printed name)
Approved by: _________________________________ |  |  |  | Date: ________________
(Signature over printed name)