## Table of Contents
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table of Contents
NGA Name
As of December 31, 2017
Project Factsheet
Table 1 | Agency Organizational Structure in the Implementation of ODA Projects (with Organizational Chart and Assigned Officials)
Table 2 | Regional Disaggregation of Projects and Programs
Table 3A | Financial Status of Projects and Programs
Table 3B | Budget Forecast
Table 3C | Loan Disbursement (Withdrawal) Targets
Table 4A | Physical Targets and Actual Accomplishments of Projects and Programs
Table 4B | Components and Physical Outputs of Projects and Programs
Table 4C | Project/Program Component(s) Addressing Climate Change and Contributing to Disaster Risk Reduction
Table 4D | Projects/Programs with Incomplete Output(s) or Sustainability Issue(s), and Damaged Output(s)
Table 5 | Problem Analysis of Projects and Programs
Table 6 | Projects/Programs for Possible Restructuring/ICC Re-evaluation in CY 2018
Table 7 | Project/Program Results
Table 8 | Lessons Learned Register for Projects and Programs
Table 9 | Actions Taken on Recommendations Made during the CY 2017 ODA Review
Table 10 | Classification of ODA Projects by Gender-Responsiveness

## Table 1
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 1
Agency Organizational Structure in the Implementation of ODA Projects (with Organizational Chart and Assigned Officials)
NGA Name
As of December 31, 2017
Organizational Structure
Prepared by: ______________________________ | Date: ________________
(Signature over printed name)
Approved by: ______________________________ | Date: ________________
(Signature over printed name)

## Table 2
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 2
Regional Disaggregation of Projects and Programs
NGA Name
As of December 31, 2017
Project/Program Title | Location | Latest Approved Project/Program Cost (PhPM) |  |  |  | Implementation Schedule |  | Remarks
| (Region/s) |  |  |  |  | (mm/dd/yyyy)
|  | TP | LP | GP | GPH | Start1 | Completion2
Projects
Project 1 | Total | 105 | 75 | 15 | 15 | 2011-01-01 | 2017-12-31
| Region I | 70 | 50 | 10 | 10 | 2012-01-01 | 2015-12-31
| Region II | 35 | 25 | 5 | 5 | 2012-01-01 | 2015-12-31
| Region N |  |  |  |  | 2013-01-01 | 2014-12-31
Nationwide3
Unallocated
Project 2 | Total
Region I
Region II
Region N
Nationwide3
Unallocated
Programs | Total
Program 1 | Region I
Region II
Region N
Nationwide
Nationwide3
Unallocated
| LP - Loan Proceeds |  | GP - Grant Proceeds |  | GPH - Local Counterpart Fund
TP - Total Project/Program Cost
1 Start date refers to the earliest start date among the sub-projects/activities in the region for the project/program.
2 Completion date refers to the latest completion date among the sub-projects/activities in the region for the project/program.
3 Cost known to be incurred in all regions, but breakdown for each region can not be determined.
Projects are defined as special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
Programs are defined as a homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, or for the basic maintenance of the agency’s
administrative operations, or for the provision of staff support to the agency’s administrative operations, or for the provision of staff support to the agency’s line functions.
Prepared by: ______________________________ | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ | Date: _____________________________
(Signature over printed name)

## Table 3A
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 3A
Financial Status of Projects and Programs
NGA Name
As of December 31, 2017
Project/ | Fund | Allotment Releases |  |  |  | Obligations |  |  | Disbursements
Program | Category | As of | CY 20172 |  | Total Available | As of | CY |  | As of | CY
Title |  | Dec 31, 20161 | Continuing | New | To Date | Dec 31, 2016 | 2017 | Total | Dec 31, 2016 | 2017 | Total
| (1) | (2) | (3) | (4) | (6)=(3+4) | (7) | (8) | (9)=(7+8) | (10) | (11) | (12)=(10+11)
Projects
Project 1 | TP
LP
GP
GPH
Project 2 | TP
LP
GP
GPH
Programs
Program 1 | TP
LP
GP
GPH
Program 2 | TP
LP
GP
GPH
TP - Total Project Cost |  | LP - Loan Proceeds |  | GP - Grant Proceeds
1 Excluding any balance carried forward to CY 2017, which should be placed under the "Continuing" releases in CY 2017.
2 Net of any adjustments made in CY 2017
Prepared by: ______________________________ |  |  |  |  | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ |  |  |  |  | Date: _____________________________
(Signature over printed name)

## Table 3B
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 3B
Budget Forecast
NGA Name
As of December 31, 2017
The sum of the multi-year budget requirement and the obligations as of end 2017 should be equal to the current estimate of the total project cost.
Project/ | Fund | Total Cost1 |  |  |  | Multi-year Requirement Forecast
Program | Category | ICC-Approved |  | L/G | Current | 2018 |  |  |  | 2019 | 2020 | 2021 | 2022 | Future Years
Title |  | Original | Revised | Cost | Estimate | 1Q | 2Q | 3Q | 4Q |  |  |  |  | (2023 onwards)
Projects
Project 1 | TP
LP
GP
GPH
Project 2 | TP
LP
GP
GPH
Programs
Program 1 | TP
LP
GP
GPH
Program 2 | TP
LP
GP
GPH
TP - Total Project Cost |  | LP - Loan Proceeds |  | GP - Grant Proceeds
Prepared by: ______________________________ |  |  |  |  | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ |  |  |  |  | Date: _____________________________
(Signature over printed name)

## Table 3C
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 3C
Loan Disbursement (Withdrawal) Targets
NGA Name
As of December 31, 2017
Amounts should be in Original Currency. Amount in the "Total" column should equal to the Net Commitment.
Project/Program Title | Loan Original Currency | Net Commitment1 (in OC) | Availment as of Dec 2017 | 2018 Targets |  |  |  | Future Targets |  |  |  |  | Total | Remarks2
|  |  |  | Q1 | Q2 | Q3 | Q4 | 2019 | 2020 | 2021 | 2022 | Future Years 2023 onwards
| (OC) | (1) | (2) | 2018 Targets Q1: (3); Future Targets 2019: (4) |  | (5) = (2+3+4)
Projects
Project 1
Project 2
Project 3
Project N
Programs
Program 1
Program 2
Program 3
1 Loan Amount Less Cancellations
2 Indicate the foreign exchange rate(s) used in setting future targets
Prepared by: ______________________________ |  |  | Date: _______________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: _______________
(Signature over printed name)

## Table 4B
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 4B
Components and Physical Outputs of Projects and Programs
NGA Name
As of December 31, 2017
Project/Program Title | Outputs | Target |  | Actual |  | Validated | Remarks1
|  | As of 31 | CY 2017 | As of 31 | CY 2017 | Agency MFO(s)
|  | Dec. 2016 |  | Dec. 2016 |  | Supported
Projects
Project 1
| Output 1 |  |  |  |  | MFO Statement 1
Output 2
Output 3
Project 2
Output 1
Output 2
Output 3
Programs
Program 1
Output 1
Output 2
Output 3
1 Indicate whether the outputs would be delivered as scheduled, or if not, the factors that affected the delayed or non-delivery of said outputs, with the details provided in Table 5.
Prepared by: ______________________________ |  |  | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: _____________________________
(Signature over printed name)

## Table 4A
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 4A
Physical Targets and Actual Accomplishments of Projects and Programs
NGA Name
As of December 31, 2017
Project/Program Title | Target (%) |  | Actual (%) |  | Future Targets1 | [8 empty] | Status as of December 2017 (on/ahead/behind schedule, or completed)2 | Remarks3
| As of Dec 31, 2016 | As of Dec 31, 2017 | As of Dec 31, 2016 | As of Dec 31, 2017 | 2018 |  |  |  | 2019 | 2020 | 2021 | 2022 | Future Years 2023 onwards
[5 empty] | 1Q | 2Q | 3Q | 4Q
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Projects
Project 1 | 10 | 30 | 11 | 25 | 3 | 2 | 3 | 4 | 12 | 18 | 12 | 10 |  | On schedule Actual OWPA = 36% Target OWPA = 40%; 10% of target OWPA = 4p.p; On schedule if actual OWPA is between 37% and 43%
Project 2 | 50 | 20 | 25 | 18 | 4 | 2 | 3 | 4 | 15 | 14 | 15 | - |  | Behind schedule Actual OWPA = 43%; Target OWPA = 70%; 10% of target OWPA = 7p.p; Behind schedule if actual OWPA is 63% and below
Project 3 | 25 | 15 | 30 | 20 | 6 | 7 | 8 | 5 | 14 | 10 | - | - |  | Ahead schedule Actual OWPA = 50%; Target OWPA = 40%; 10% of target OWPA = 4p.p; Ahead of schedule if actual OWPA is 44% and above
Project N
Programs
Program 1
Program 2
Program N
1 Sum of columns 5 to 14 should equal to 100% (i.e., actual accomplishment as of end 2017 and future targets until the end of project implementation).
2 Indicate the physical status as of end of CY 2017, whether: completed, ahead of schedule, on schedule, or behind schedule [see guidelines on how to determine physical status based on the Overall Weighted Physcal Accomplishment (OWPA).]
3 Indicate whether the project would be completed on schedule. In case no physical accomplishment or output, please indicate preparatory activities undertaken. If there is negative slippage as of end of CY 2017, cite reason(s) with the details provided in Table 4A.
Prepared by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: ________________
(Signature over printed name)

## Table 4C
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 4C
Project/Program Component(s) Addressing Climate Change and Contributing to Disaster Risk Reduction
NGA Name
As of December 31, 2017
(Kindly indicate the component/s of projects and programs that address climate change mitigation/adaptation or disaster risk reduction by indicating the cost/amount
allocated for each initiative).
Project Title | Initiative Amount (PM) |  |  | Total | Remarks2
| Climate Change1 |  | DRR
| Adaptation | Mitigation
Projects
Project 1 (Sample) |  |  |  |  | Engineering designs include measures for erosion control and reduction of soil degradation.
Component 1: | 0.1 | 0.3 |  | 0.4
Component 2: |  |  | 5.5 | 5.5
Component N |  |  | 2 | 2
Programs |  |  |  | 0
Program 1 |  |  |  | 0
Component 1: |  |  |  | 0
Component 2: |  |  |  | 0
0
0
Component N |  |  |  | 0
1Climate Change Initiatives (National Framework Strategy on Climate Change 2010-2022):
Mitigation - aims to facilitate the transition towards low greenhouse gas emissions for sustainable development
a) energy efficiency and conservation; b) realization of the full potential of the country’s renewable energy; c) improvement of the transport sector through the uptake of
alternative fuels and expansion of mass transport systems; d) making use of energy--efficient design and materials for public infrastructure and settlements; e)
reduction of emissions from deforestation and forest degradation; and g) waste management.
Adaptation - points towards building the adaptive capacity of communities and increasing the resilience of natural ecosystems to climate change
a) enhancement of vulnerability and adaptation assessments; b) integrated ecosystem-based management; c) water governance and management; d) promotion of a
climate-responsive agriculture; e) support climate-responsive health sector; and f) encourage climate-proofing infrastructure
2Disaster Risk Reduction (Republic Act No. 10121) - the concept and practice of reducing disaster risks through systematic efforts to analyze and manage the causal factors
of disasters, including through reduced exposures to hazards, lessened vulnerability of people and property, wise management of land and the environment,
and improved preparedness for adverse events.
3Description of CC/DRR initiatives under the relevant component(s) of the project/program.
Prepared by: ______________________________ |  |  | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: _____________________________
(Signature over printed name)

## Table 4D
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 4D
Projects/Programs with Incomplete Output(s) or Sustainability Issue(s), and Damaged Output(s)
NGA Name
As of December 31, 2017
Closed projects/programs in CY 2017 with incomplete outputs or sustainability issues
Project/Program Title | Year Completed | Description of the Incomplete Output(s) or Sustainability Issues* | Actions taken/ being taken to address the incomplete output(s) | Actions to be taken to address the incomplete output (s)
Projects
Programs
Ongoing/closed projects/programs with damaged outputs caused by man-made and natural disasters in CY 2017
Project/Program Title | Year Completed | Description of Damaged Output(s)* | Actions taken/ being taken to address the damaged output(s) | Actions to be taken to address the damaged output(s)
Projects
Programs
* with attribution to specific events (e.g. Typhoon Vinta)
Prepared by: ______________________________ |  |  | Date: _____________________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: _____________________________
(Signature over printed name)

## Table 5
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 5
Problem Analysis of Projects and Programs
NGA Name
As of December 31, 2017
Project/ Program | Issue Details (Root Cause Issue) | Problem/ Issue Typology1 | Issue Status (Current or Resolved) | Actions Taken/Being Taken based on Recommendations in CY 2016 Porfolio Review2 | Updates on Actions Taken/Being Taken | Actions to be Taken in CY 2018 and Beyond3 | Remarks4
Projects
Project 1
Project 2
Project N
Programs
Program 1
Program 2
Program N
1Use typology of issues indicated in the Guidelines
2For both current or outstanding issues/problems and those which ended in 2017, include actions taken/being taken by the agency on recommendations during the CY 2016 ODA Portfolio Review
3Plan of action to address currrent or outstanding issues/problems.
4For problems identified as current or outstanding, if any, and discuss the probability of achieving project objectives (i.e., low, moderate, or high)
Prepared by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: ________________
(Signature over printed name)

## Table 6B (hidden)
For GFIs
CY 2014 ODA Portfolio Review
Table 6B
Assumptions/Risk Register for (Project Title)
GOCC Name
Outcome level | Assumptions/Risk Category | Assumptions/Risk Description (Potential Impacts on Project Competion) | Management Strategies/ Contingency Measures | Risk Status (current or ended) | Remarks
(1) | (2) | (3) | (4) | (5) | (6)
Goal
Purpose
Output | example: | example: | example: | Current | example:
| Operation and Maintenance of the IS | a) Farmer Irrigation Organizations (FIO) operationalized | a) Additional personnel for organizing are being hired. |  | FIOs expected to sustain O&M of completed facilities
|  | b) NIA acceptance of completed project from contractor | b) PMO regular supervision of the work of the contractor to avoid rejection of the work done.
|  | c) O&M training provided | c) Ensure availability of NIA personnel to conduct the training
Activities | example: | example: | example: |  | example:
| Start-up delays | Non-familiarity with budget policies by project management staff/personnel will extend preparation of budget delaying availability of funds | Start-up activities include briefing/coaching of all financial management personnel. | Current | Ongoing familiarization
|  | Unfamilairity on procurement procedures including the preparation of bid docmuments | Training of personnel on procurement law and bidding procedures before the start of project
Prepared by: ______________________________ | Date: ________________
(Signature over printed name)
Approved by: _________________________________ | Date: ________________
(Signature over printed name)

## Table 6
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 6
Projects/Programs for Possible Restructuring/ICC Re-evaluation in CY 2018 (if applicable)
NGA Name
As of December 31, 2017
Project/Program Title | Details of Possible Project Re-structuring/ | Reason(s)/Justification(s)
ICC Re-evaluation in CY 2018
Projects
Project 1
Project 2
Project N
Programs
Program 1
Program 2
Program N
Prepared by: ______________________________ |  | Date: ________________
(Signature over printed name)
Approved by: ______________________________ |  | Date: ________________
(Signature over printed name)

## Table 9B (hidden)
CY 2014 PORTFOLIO REVIEW
Table 9B
Funds Flow Timelines
GFI Name
As of December 31, 2014
Project Title/Funding Source | WA Amount Requested (US$M) | Withdrawal Application (WA) |  |  | BTr Notice |  | NCA Processing |  |  | Total Processing Time from WA to NCA Release (No. Of Days)
|  | WA Applied (Date Received by FS) | WA Release (Date Received by BTr) | WA Application to Release (No. Of Days) | BTr Notice (Date Received by IA) | WA Release to BTr Notice (No. Of Days) | Application for NCA (Date Received by DBM) | NCA Release Date (Received by IA) | BTr Notice to NCA Release (No. Of Days)
|  | (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9= 3+5+8)
Agency Total
Project 1
Withdrawal Application No. ___
Withdrawal Application No. ___
Withdrawal Application No. ___
Project 2
Withdrawal Application No. ___
Withdrawal Application No. ___
Withdrawal Application No. ___
Project 3
Withdrawal Application No. ___
Withdrawal Application No. ___
Withdrawal Application No. ___
Project N
Withdrawal Application No. ___
Withdrawal Application No. ___
Withdrawal Application No. ___
Prepared by: ______________________________ |  | (1): Date: _______________
(Signature over printed name)
Approved by: ______________________________ |  | (1): Date: _______________
(Signature over printed name)

## Table 9A (hidden)
Project Title: _________________________________________
GFI Name : _________________________________________
CY 2014 ODA PORTFOLIO REVIEW
Table 9A
PROCUREMENT MILESTONES (with contracts awarded or NTP issued in CY 2014)
|  | CONTRACT DESCRIPTION | START OF TENDERING PROCESS/ ADVERTISE-MENT | SUBMISSION AND OPENING OF BIDS | COMPLETION OF BID EVALUATION |  | CONTRACT AWARD | ISSUANCE OF NOTICE TO PROCEED | TOTAL | CONCURRENCE OF FUNDING INSTITUTION** | NET OF FUNDING INSTITUTION'S PROCESSING TIME
[5 empty] | Technical | Financial |  |  | (no. of months)
|  |  | (mm/dd/yy) | (mm/dd/yy) | (mm/dd/yy) | (mm/dd/yy) | (mm/dd/yy) | (mm/dd/yy) |  | (no. of months) | (no. of months)
|  |  | (1) | (2) | (3) | (4) | (5) | (6) | (7=1+2+3+4+5+6) | (8) | (9=7 - 8)
Consulting Services
* | Contract Name/ Procurement Guidelines Used:
Amount (--M)
Accomplishment Date:
Target
Actual
Remarks
Civil Works
* | Contract Name/ Procurement Guidelines Used:
Amount (--M)
Accomplishment Date:
Target
Actual
Remarks
Goods (Equipment/Materials)
* | Contract Name/ Procurement Guidelines Used:
Amount (--M)
Accomplishment Date:
Target
Actual
Remarks
* Major Contracts awarded or NTP issued in 2008 (pls. use extra pages to reflect all major contracts)
** Indicate concurrence of Funding Institutions from the start of the tendering process up to contract award
Prepared by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: ________________
(Signature over printed name)

## Table 7
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 7
Project/Program Results
NGA Name
As of December 31, 2017
Project/Program Title : _______________________________________________________________________
Contributes to (please check all applicable)
SDG | :
0+10 Agenda | :
Objectives | Results Indicator/Target | Actual | Alignment to PDP-RM 2017-2022 Results Indicators 1
(Based on Logframe) | (Based on Logframe) | (Using Proxy or Logframe Indicators)
Goal: |  |  | Goal
Objective statement (goal) | Indicator Target 1 (goal) | Actual Value for Indicator Target 1 (goal) as of (date)
| Indicator Target 2 (goal) | Actual Value for Indicator Target 2 (goal) as of (date)
| Indicator Target N (goal) | Actual Value for Indicator Target N (goal) as of (date)
Outcome: |  |  | Outcome
Objective statement (outcome) | Indicator Target 1 (purpose) | Actual Value for Indicator Target 1 (purpose) as of (date)
| Indicator Target 2 (purpose) | Actual Value for Indicator Target 2 (purpose) as of (date)
| Indicator Target N (purpose) | Actual Value for Indicator Target N (purpose) as of (date)
Output
Outputs: | End-of-Project Indicator Target 1 (output) | Actual Value for EOP Indicator Target 1 (output) as of (date)
| End-of-Project Indicator Target 2 (output) | Actual Value for EOP Indicator Target 2 (output) as of (date)
| End-of-Project Indicator Target N (output) | Actual Value for EOP Indicator Target N (output) as of (date)
1 May be downloaded using this link: http://www.neda.gov.ph/philippine-development-plan-results-matrices-2/philippine-development-plan-results-matrices-2017-2022/
Prepared by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: ________________
(Signature over printed name)
1
2
3
4
5
6
7
8
9
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
10
0

## Table 8
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 8
Lessons Learned Register for Projects/Programs
NGA Name
As of December 31, 2017
Project/Prgoram Title | Project/Program Management Area/Category | Project/Program Phase | Situation | Lessons Learned*
`
Project 1 | Procurement | Implementation | Some items will not be delivered by the Contractor because these are not clearly specified in the signed contract. | In preparing the contract, make sure that the deliverables of the contractor are specific and specified clearly in details to avoid misunderstanding. Be sure that information are accurate and no gray areas before signing the contract.
Project 2
Project N
Programs
Program 1
Program 2
Program N
*Lessons learned for CY 2017 only.
Prepared by: ______________________________ |  |  | Date: _______________
(Signature over printed name)
Approved by: ______________________________ |  |  | Date: _______________
(Signature over printed name)

## Table 9
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 9
Actions Taken on Recommendations Made during the CY 2016 ODA Review
NGA Name
As of December 31, 2017
Project/Program Title | CY 2016 ODA Review | Timelines | Responsibility Center | Actions Taken
Recommendation(s)
Projects
Project 1
Project 2
Project N
Programs
Program 1
Program 2
Program N
Prepared by: ______________________________ |  |  |  | Date: ________________
(Signature over printed name)
Approved by: ______________________________ |  |  |  | Date: ________________
(Signature over printed name)

## Table 10
For NGAs
CY 2017 AGENCY PORTFOLIO REVIEW
Table 10
Classification of ODA Projects by Gender-Responsiveness
NGA Name
As of December 31, 2017
Project Title/Duration (1) | Classification by gender-responsiveness (2) |  | Gender issues identified (3) | How the project is addressing identified gender issues (4)
| PD* | PIMME**
| (2-a) | (2-b)
*PD – Project Design
** PIMME – Project Implementation, Management, Monitoring and Evaluation
Note: Interpretation of score (based on Box 7 [for Table 1 (2a)] and Boxes 16 and 17 [for Table 1 (2b)] of the Harmonized Gender and Development
Guidelines on Project Development, Implementation, Monitoring and Evaluation (HGDG). For the purpose of the monitoring template, letter
codes have been added to the gender-responsive score, as follows:
| 0 - 3.9 | D | Gender and development (GAD) is invisible in the proposed project
| 4.0 - 7.9 | C | Project has promising GAD prospects
| 8.0 - 14.9 | B | Project is gender-sensitive
| 15.0 - 20.0 | A | Project is gender-responsive
For details, please refer to the Harmonized GAD Guidelines, Second Edition (may be downloaded at www.neda.gov.ph).
Prepared By: __________________________________ |  |  |  | Date: ________________
(Signature Over Printed Name)
Approved By: __________________________________ |  |  |  | Date: ________________
(Signature Over Printed Name)
GUIDE IN ACCOMPLISHING THE MATRIX
(with examples from the Agrarian Reform Infrastructure Support Project Phase III – Note that the examples are just meant to facilitate the
process. The actual information based on the project provided by the responsible implementing agency may differ from the examples below).
(1) Project title/duration
• Complete project title
• Duration of the project beside the title, preferably using format Month Year
• Example: Agrarian Reform Infrastructure Support Project Phase III (ARISP III) March 2007 to March 2013
(2) Classification by gender-responsiveness
(2-a)
• Rate the project design as “Invisible”, “Promising”, “Gender-sensitive”, or ”Gender-responsive” using Box 7 of the HGDG. For the purpose of Table 1,
use the code provided in the footnote of the table.
(2-b)
• Rate the project management and implementation, and monitoring and evaluation using Boxes 16 and 17 of the HGDG Checklist for Project Implementation
and Management, Monitoring and Evaluation.
(3) Gender issues identified
• State the gender issue/s identified or suggested in the project document. If no gender issue was identified, state “no gender issue identified”.
o Example of gender issue identified in ARISP: Women’s role in fetching water from springs and wells (Note this was not specified as a gender issue per se
in the proposal but the project has a subcomponent to alleviate current problems of women and children in the community in terms of fetching water from nearby sources).
(4) How is the project addressing identified gender issues
• Example of gender issue addressed: The Potable Water Supply Development Subcomponent seeks to minimize the time spent by women and children in hauling
water from the springs and wells at least 50 percent.